项目进度表(二)

SUMMARY OF SOURCES AND USES OF FUNDS BY PROJECT COMPONENT Ⅱ

（三）贷款协定执行情况表

iii. Statement of Implementation of Loan Agreement

贷款协定执行情况表

STATEMENT OF IMPLEMENTATION OF LOAN AGREEMENT

（四）指定账户报表

iv. Designated Account Statement

指定账户报表

Designated Account Statement

（五）财务报表附注

财务报表附注

1.项目概况

1.1吉林省世行贷款农产品质量安全项目贷款号：7899－CN；《贷款协定》已于2010年7月20日签订。项目总投资为971,990,000.00元人民币（美元与人民币汇率按1：6.8计算），其中利用世行贷款100,000,000.00美元，贷款期限27年（含宽限期8年），执行世界银行浮动利差贷款利率。

1.2项目总体目标：该项目围绕农产品质量安全保障体系，引进并推广农业标准化生产技术规程，加强对农产品的检测和监管，最大程度减少农产品安全风险，提高生产者和消费者的安全生产和消费意识，全面提升吉林省农产品质量安全水平。

1.3子项目分类说明:项目内容包括两大类五个子项目，第一类是公益性建设项目：包括4个子项目：子项目A：农产品质量安全标准农业规程推广;子项目B：农产品质量安全的公共监测;子项目C：农产品质量安全应用研究、培训和宣传；子项目 E：项目管理和监测。第二类是非公益性生产经营项目（含1个子项目D：安全农产品生产链示范模式）。子项目B 为实体工程，其他子项目均不能形成实体工程，是通过宣传、培训、示范、项目管理等手段来提高对农产品生产、加工、销售全过程质量安全的意识。

2.报表编制范围

根据吉林省世行贷款农产品质量安全项目《贷款协定》和《项目协定》，吉林省世行贷款农产品质量安全项目领导小组办公室为本项目执行机构，吉林省债务管理服务中心(简称：省债务中心)为本项目专用账户管理部门。

3.主要会计政策

3.1会计核算年度采用公历年制，即公历每年1月1日至12月31日。

3.2本项目会计核算执行财政部《世界银行贷款项目会计核算办法》（财际字〔2000〕13号文件）和《吉林省世行贷款农产品质量安全项目财务管理与会计核算办法（试行）》（吉财农发〔2010〕893号文件）等制度，以权责发生制作为核算基础，采用借贷复式记账法记账，以人民币为记账本位币。

3.3外币以辅助账核算，年末按照中华人民共和国财政部规定汇率（1美元＝6.1190元人民币）调整外债并核算汇兑损益。

4.报表科目说明

4.1项目支出情况

截止到2014年末，全省项目共计支300,776,173.78元，,其中子项目A总支出28,252,140.98元，约占该子项目总投资的22.09％；子项目B总支出125,320,597.73元，约占该子项目总投资的27.39%；子项目C总支出46,831,407.16元,约占该子项目总投资的49.64%；子项目D总支出73,261,917.32元，约占该子项目总投资的37.71%；子项目E总支出27,110,110.59元，约占该子项目总投资的27.70%。

4.2货币资金

2014年12月31日货币资金余额为人民币199,121,737.19元，比上年增加人民币28,219,867.61元。

4.3预付及应收款

2014年12月31日余额为人民币7,528,080.73元，主要是2014年吉林省世行项目办统一采购货物按合同支付给供货商的采购预付款。

4.4项目拨款

截止到2014年末，全省项目办账户国内配套资金共计到位250,732,871.49元。

4.5世行贷款

截止到2014年末，全省项目办共计提取世行贷款37,924,283.36美元（含世行直接支付）;周转金账户设在外债中心。

4.6应付款

2014年12月31日余额为人民币20,164,630.13元，主要是吉林省邮电规划设计院有限公司质量保证金、惠诺德（北京）科技有限公司履约保证金、清华同方公司的履约保证金，以及吉林省世行项目办统一采购的超低温冰箱未支付给供应商的采购款。

4.7留成收入

2014年12月31日余额人民币4,199,800.20元，主要是银行存款利息收入。

5.其他说明事项

对不能形成实体工程的子项目（如：子项目A、子项目C和子项目E全部属于支出费用），我们选用了“其他投资”“待摊投资”，按照子项目分别归集支出核算投资成本，待项目建设期结束时分五个子项目进行决算。另外，对该项目银行存款产生的利息收入，选用“留成收入”进行核算。

v. Notes to the Financial Statements

Notes to Financial Statements

1.Project Overview

1.1 The Loan No. of Jilin Provincial Agricultural Products Quality Safety Project Financed by the World Bank Loan is 7899-CN. The Loan Agreement was signed on July 20, 2010. The total investment of the project is RMB 971,990,000.00 yuan (exchange rate of USD and RMB: 1: 6.8), including the World Bank loan of 100,000,000.00 USD, with the loan period of 27 years (including the grace period of 8 years)and the floating margin loan interest rate of the World Bank implemented.

1.2 Overall objectives of the project: The project, focused on the agricultural products quality safety support system, is to introduce and popularize the agricultural standard production technology specification, strengthen the testing and monitoring of agricultural products, reduce the safety risks of agricultural products, to the maximum extent, improve the producers’ and consumers’ awareness of safety in production and consumption and comprehensively upgrade the agricultural products quality safety level of Jilin Province.

1.3 Description of classification of sub-projects: The project includes 5 sub-projects in two categories. The first category include the public welfare construction sub-projects: 4 sub-projects: Sub-project A: Popularization of Agricultural Products Quality Safety Standard Agricultural Specification; Sub-project B: Public Monitoring of Agricultural Products Quality Safety; Sub-project C: Research, Training and Publicity of Agricultural Products Quality Safety Application; Sub-project E: Project Management and Monitoring; the second category includes the non-public-welfare production and operation projects (including 1 Sub-project D: Safe Agricultural Products Production Chain Demonstration Mode). The Sub-project B is an entity project and other sub-projects, all of which are not the entity projects, are to improve the quality safety awareness in the whole process of production, processing and sales of agricultural products by means of publicity, training, demonstration and project management, etc.

2.Establishment Scope of the Statements

In accordance with the Loan Agreement of Jilin Provincial Agricultural Products Quality Safety Project Financed by the World Bank Loan and the Project Agreement, the Office of the Leading Group of Jilin Provincial Agricultural Products Quality Safety Project Financed by the World Bank Loan is the executive agency of the project and Jilin Provincial Debts Management Service Center (hereinafter referred to as the Provincial Debts Center) is the special account administration department of the project.

3.Main Accounting Policies

3.1 In accounting practice, the Gregorian calendar year is adopted as the fiscal year from January 1 to December 31.

3.2 In the accounting of the project, the Accounting Methods for the World Bank Financed Project（Caijizi[2000]No.13）and Financial Management and Accounting Methods for Jilin Provincial Agricultural Products Quality Safety Project Financial by the World Bank Loan (Provinsional) (JCNF [2010] No. 893) are implemented. The accrual basis and the debit/credit double entry bookkeeping method are adopted. RMB is used as the recording currency of bookkeeping.

3.3 The accounting of foreign currencies is made through the auxiliary accounts and the foreign debts is adjusted and the accounting of exchange profit and loss is made according to the exchange rate (1USD = 6.1190 RMB Yuan) stipulated by the Ministry of Finance of the People’s Republic of China at the end of the year.

4.Explanation of Subjects

4.1 Project expenditures

By the end of 2014, the total project expenditure in the whole province has been 300,776,173.78 yuan, including the total Sub-project A expenditure of 28,252,140.98 yuan, accounting for 22.09% of the total investment of the sub-project; the total Sub-project B expenditure of 125,320,597.73 yuan, accounting for 27.39% of the total investment of the sub-project; the total Sub-project C expenditure of 46831407.16 yuan, accounting for 49.64% of the total investment of the sub-project; the total Sub-project D expenditure of 73,261,917.32 yuan, accounting for 37.71% of the total investment of the sub-project; the total Sub-project D expenditure of 2,110,110.59 yuan, accounting for 27.70% of the total investment of the sub-project;

4.2 Monetary funds

The balance of the monetary funds was RMB 199,121,737.19 yuan on December 31, 2014, RMB 28,219,867.61 yuan more than that in the previous year.

4.3 Prepaid and Receivable

Its balance on December 31, 2014 was RMB 7,528,080.73 yuan, mainly the prepayment to the suppliers for the goods uniformly purchased by Jilin Provincial World Bank Project Office according to the contracts in 2014.

4.4 Project appropriation funds

The total domestic counterpart fund in the account of the provincial project office has been RMB 250,732,871.49 yuan by the end of 2014.

4.5 World Bank loan

The total loan of the World Bank withdrawn by the provincial project office has been 37,924,283.36 USD (including the direct payment of the World Bank) by the end of 2014; the circulating fund account is set in the Debts Center.

4.6 Payable

The balance on December 31, 2014 was RMB 20,164,630.13 yuan, mainly the quality assurance fund to Jilin Provincial Design Institute of Posts and Telecommunications Planning, the performance bond to Respect (Beijing) Science and Technology Co., Ltd., the performance bond to Tsinghua Tongfang Co., Ltd. and the payment unpaid to the supplier by Jilin Provincial World Bank Project Office uniformly purchasing the ultra-low temperature refrigerators.

4.7 Retained Earnings

The balance on December 31, 2014 was RMB 4,199,800.20 yuan, mainly interest earned of bank deposit.

5.Other Explanation

For the sub-projects which are not the entity projects (such as Sub-project A, Sub-project C and Sub-project E, all of which need the expenditure), we chose “other investment” and “investment to be amortized” to summarize and collect the expenditure for the accounting of the investment cost according to the sub-projects and then carry out final accounting according to 5 sub-projects after the construction period expired. In addition, the “retained income” was chosen for the accounting of the interests earned in the bank deposit of the project.

三、审计发现的问题及建议

审计发现的问题及建议

除对财务报表进行审计并发表审计意见外，审计中我们还关注了项目执行过程中相关单位国家法规和项目贷款协定遵守情况、内部控制和项目管理情况、项目绩效及上年度审计建议整改落实情况。我们发现存在如下问题：

（一）多计待摊投资118,409.00元

2014年1月至12月，吉林省世行贷款农产品质量安全项目管理办公室将吉林省财政厅拨入吉林省农业综合开发办公室的事业经费118,409.00元，在项目中核算计入项目其他待摊投资，形成多计待摊投资118,409.00元。

违反了《中华人民共和国会计法》第九条“各单位必须根据实际发生的经济业务事项进行会计核算，填制会计凭证，登记会计账簿，编制财务会计报告”的规定。建议省项目办调整相关账目。

（二）中期调整投资计划未得到省发改委审批

2010年11月，我省世行贷款农产品质量安全项目经省发改委批准总投资97,199.02万元， 2014年，由于部分子项目投资内容变化，在未得到省发改委批准的情况下，省世行办估算总投资为95,036.19万元，比原计划减少2,162.82万元。其中，标准化（良好农业操作规范）示范推广项目减少3,989.47万元，农产品质量安全公共监测项目增加5,387.28万元，农产品质量安全应用技术研究、培训和公共宣传项目减少417.96万元，农业品质量安全生产链模式示范项目增加4,211.03万元，项目管理、监测与评价增加102.08万元，工程建设其它费用增加379.59万元，实施期财务费用减少3,028.40万元。2015年4月，吉林省发改委已对项目中期调整进行批复，建议省项目办尽快落实调整计划。

（三）农民培训项目管理不规范

2011年12月9日，德惠市世界银行贷款农产品质量安全项目—培训机构采购项目，经政府采购确定德惠市农村能源技术服务站为中标人。12月9日，德惠市世行办与德惠市农村能源技术服务站签订了培训项目协议书，培训费用为257,000.00元，培训时间为2011年12月10日至2012年1月18日，培训任务为培训178名村干部及1,750名农民，培训内容为农产品质量安全相关知识。德惠市农村能源技术服务站完成了2011年度、2012年度及2013年度村干部及农民培训任务，德惠市世行办已将2011年度、2012年度培训费用257,000.00元、164,500.00元拨付德惠市农村能源技术服务站，2013年度培训费用173,250.00元，已向省世行办提请报账，尚未拨付。通过检查费用支出、培训内容及影像资料，发现在农民培训中培训教材未完全发放到位，培训项目管理不够规范。建议德惠市项目办监督德惠市农村能源技术服务站完善培训内容，规范培训操作。

（四）设备闲置16台

2014年，梅河口市农产品质量安全项目计划采购监测信息系统支撑设备69台套价值430,000.00元，由省世行办统一负责采购。截至2015年5月，实际到位设备69台，其中：台式电脑24台，数码相机22台，传真机20台，数码摄像机3台。由于省农委监测信息系统和安全检测体系建设项目尚未完成，上述设备只发放53台，闲置16台，其中：数码相机闲置9台、传真机6台、数码摄像机1台。建议省项目办督促省农委尽快完成监测信息系统和安全检测体系建设项目，按项目要求尽快发放闲置设备。

（五）设备采购内容、项目建设内容和项目可研不符

（1）2012年1月，吉林省佳庆米业有限公司委托吉林省绿色食品工程研究院编制《东丰县佳庆大米安全生产链模式示范项目可行性研究报告》。项目总投资814.88万元，其中利用世行贷款500万元，建设内容为购置先进加工生产线一条，附属设备3台套。同年5月，项目获得通过评审开始正式实施。2013年4月和11月，东丰县农发办分2笔拨付吉林省佳庆米业有限公司贷款资金4,864,768.38元。经现场监盘，项目单位实际采购设备价格、数量、型号与项目可研报告存在差异，如：计划采购色选机2台150万元，实际采购色选机4台24万元，设备型号也发生变更；计划采购立式沙辊米机3台54万元，实际采购1台36,800元。

（2）2012年1月，梅河口市兴达米业有限责任公司委托吉林省绿色食品工程研究院编制《梅河口市佳庆大米安全生产链模式示范项目可行性研究报告》。项目总投资800万元，其中利用世行贷款500万元，建设内容为购置色选机、抛光机及冷藏设备等8台套和新建保鲜库1,000㎡、仓储库2,000㎡。同年5月，项目获得通过评审开始正式实施。2014年，梅河口农发办分2笔拨付梅河口兴达米业有限责任公司贷款资金4,788,439.43元。经现场监盘，项目单位实际采购设备价格、数量、型号与项目可研报告存在差异，保鲜库、仓储库建筑面积小于可研设计，如：保鲜库实际建筑面积800.23㎡，仓储库实际建筑面积1,733.69㎡；采购色选机3台36.6万元，抛光机1台7.2万元，其他设备未进行采购。

（3）2010年9月，辽源市夏兴健康产业高效生物有限公司委托吉林省绿色食品工程研究院编制《辽源市夏兴黑木耳露安全生产链模式示范项目可行性研究报告》。项目总投资800万元，其中利用世行贷款500万元，建设内容为新建低温保鲜库一座（附属设备）及购置仪器设备8台套。2011年11月，项目获得通过评审开始正式实施。2013年3月和2014年1月，辽源市财政局农发办分2笔拨付辽源市夏兴健康产业高效生物有限公司贷款资金4,783,289.00元。经现场监盘，项目单位实际采购设备价格、数量、型号与项目可研报告存在差异，如：计划采购液位检测设备1台12万元、真空度检测设备1套46万元、全自动冲灌封机组1套120万元、检测检验设备60.40万元、低温保鲜库设备83.6万元，实际采购全自动灌制机一套、全自动纸箱包装机一套、卸瓶垛一台。上述设备采购变更均未通过省农发办批准；项目批复应新建低温保鲜库一座，建筑面积500平方米，投资额130万元，夏兴公司项目申报以前实际已建造保鲜库一座，企业根据需要未按实施计划新建低温保鲜库，贷款资金企业实际用于购置低温冷藏设备及支付以前年度基建工程款。

（4）2013年7月，德惠市新原粮食加工有限公司委托吉林省轻工业设计院编制《德惠市新原稻米安全生产链模式示范项目可行性研究报告》。项目总投资1,145.29万元，其中利用世行贷款500万元，建设内容为新建成品库1,500平方米1座，筒仓20个，硬质地面4,700平方米，利旧建设大米加工车间600平方米。2013年11月，项目获得通过评审开始正式实施。经现场监盘，项目单位实际土建项目与项目可研报告存在差异，应建直径10米筒仓20个，造价96万元，实际建设长60米、宽34米、储粮总量为10,000吨罩棚仓一座，工程造价98万元。上述产业链项目实施内容虽然与调整计划一致，但由于上述项目实施过程较长，设备采购内容、项目建设内容与可研报告不符，项目存在无法达到预期效果的风险。建议省项目办对后续生产链项目变更手续进行严格审查，保证项目实施效果达到可研要求。

III. Audit Findings and Recommendations

Audit Findings and Recommendations

In addition to performing the audit and expressing an opinion on the financial statements, we also make observations with respect to compliance with applicable provisions of state laws and regulations and the loan agreement of the relevant entities, its internal financial control and project management, project performance and the follow-up of previous recommendations during the project implementing process. We found the following issues:

(I)Overstating the Deferred Investment, totaling RMB 118,409.00 yuan

From Jan. to Dec. 2014, the Management Office under Leading Group for Jilin Agricultural Product Quality and Safety Project Funded by the World Bank included RMB 118,409.00 yuan of enterprise funds from Jilin Provincial Finance Department under the Other Deferred Investment, which overstated the Deferred Investment, totaling RMB 118,409.00 yuan.

It violates the provisions of the Article 9, Accounting Law of the People's Republic of China which stipulates that any unit must carry out the accounting calculation, fill in the accounting documents, register the accounting books and prepare the accounting report on the base of the economic transaction matters that actually occurred. We suggest that Jilin PMO adjust the relevant items of the account.

(II)Adjustment of the investment plans in the mid-term without obtaining the approval from the Jilin DRC

In Nov. 2010, subject to the approval of Jilin DRC, the total investment of Jilin Agricultural Product Quality and Safety Project Funded by the World Bank was RMB 971,990,200.00 yuan. In 2014, due to changes in the investment contents for some sub-projects, without obtaining the approval from the Jilin DRC, the total estimated investment was RMB 950,361,900.00yuan which was RMB 21,628,200.00 yuan less than the original planned investment. For the Standardization (good agricultural practices) Demonstration Project, it reduced RMB 39,894,700.00yuan. For the Agricultural Product Quality and Safety Public Monitoring Project, it increased 53,872,800.00yuan. For the Agricultural Product Quality and Application Technology Research, Training and Public Propaganda Project, it reduced RMB 4,179,600.00 yuan. For the Agricultural Product Quality and Safety Production Chain Model Demonstration Project, it increased RMB 42,110,300.00 yuan. For the Project Management, Monitoring and Evaluation, it increased RMB 1,020,800 yuan. For the other expenses on the project construction, it increased RMB 3,795,900.00 yuan. For the financial expenses during the period of implementation, it reduced RMB 30,284,000 yuan. In April 2015, Jilin DRC approved the project changes in the mid-term. We suggest that Jilin PMO implement the plans on changes as early as possible.

(III)Farmer Training Project without standardized management

On Dec. 9, 2011, for the Training Institution Project under Dehui City Agricultural Product Quality and Safety Project Funded by the World Bank, after the procurement by the government, the successful bidder was Dehui City Rural Energy Technology Service Station. At the same day, Dehui PMO and Dehui City Rural Energy Technology Service Station signed an agreement for the Training Project with the contract price of RMB 257,000.00.00 yuan and the training period from Dec. 10, 2011 to Jan. 18, 2012. The training tasks were to train 178 village cadres and 1,750 farmers. The training contents were the knowledge related to the agricultural products quality and safety. Dehui City Rural Energy Technology Service Station has completed the village cadres and farmers training tasks for Year 2011, Year 2012 and Year 2013 and Dehui PMO has paid RMB 257,000.00 yuan and RMB 164,500.00 yuan to Dehui City Rural Energy Technology Service Station as the training expenses for Year 2011 and those for Year 2012 respectively. For RMB 173,250.00 yuan of the training expenses for Year 2013, the withdrawal application has been submitted to the Management Office under Leading Group for Jilin Agricultural Product Quality and Safety Project Funded by the World Bank but the money has not been disbursed yet. After checking the expenditures, the training contents and image data, we found that training materials for the farmer training weren’t available completely and the management of the Training Project failed to be standardized. We suggest that Dehui PMO supervise Dehui City Rural Energy Technology Service Station to perfect the training contents and standardize the training operations.

(IV) 16 Equipments leaving unused

In 2014, Meihekou City Agricultural Product Quality and Safety Project planned to procure 69 sets of the supporting equipments for the monitoring information system with the amount of RMB 430,000.00 yuan. The Management Office under Leading Group for Jilin Agricultural Product Quality and Safety Project Funded by the World Bank was responsible for procuring the equipments uniformly. By May 2015, actually, 69 sets equipments have been put in place, of which 24 desktop computers, 22 digital cameras, 20 fax machines and 3 video cameras. Since the monitoring information system and safety testing system construction project of the Jilin Agricultural Commission hasn’t completed yet, among them, only 53 sets of equipments have been given out and the remaining 16 equipments still left unused which included 9 digital cameras, 6 fax machines and one video camera. We suggest that Jilin PMO urge the Jilin Agricultural Commission complete the monitoring information system and safety testing system construction project as early as possible and give out the unused equipments in accordance with the project requirements as early as possible.

(V)The contents of equipment procurement and contents of project construction are not in conformity with the Feasiblilty Study Report of the project.

（1）In Jan. 2012, Jilin Province Jiaqing Rice Co., Ltd. entrusted Jilin Province Green Food Engineering Design Institute to prepare the Feasibility Study Report for Dongfeng County Jiaqing Rice Safety Production Chain Model Demonstration Project. The total investment of the project was RMB 8,148,800 yuan, of which RMB 5 million yuan from the World Bank loans. The construction contents included procurement of an advanced processing production line and 3 sets of accessory equipments. In May 2012, the project officially started to implement after passing evaluation. Dongfeng County Agricultural Development Office appropriated RMB 4,864,768.38 yuan to Jilin Province Jiaqing Rice Co., Ltd. twice in April 2013 and Nov. 2013 respectively. After the site checking, there existed the difference between the price, quantities and model of the equipments actually procured by the IA with those stipulated in the Feasibility Study Report. For example, it planned to procure 2 color sorting machines with the amount of RMB 1.5 million yuan but actually, 4 color sorting machines were procured with the amount of RMB 240,000 yuan and different models and it planned to procure 3 vertical sand rollers with the amount of RMB 540,000 yuan but actually, one vertical sand roller was procured with the amount of RMB 36,800 yuan.

（2）In Jan. 2012, Meihekou City Xingda Rice Co., Ltd. entrusted Jilin Province Green Food Engineering Design Institute to prepare the Feasibility Study Report for Meihekou City Jiaqing Rice Safety Production Chain Model Demonstration Project. The total investment of the project was RMB 8 million yuan, of which RMB 5 million yuan from the World Bank loans. The construction contents included procurement of 8 sets of equipments such as color sorting machines, polishing machines, refrigeration equipments, etc., newly construction of a fresh storage with the construction area of 1,000㎡ and a warehouse with the construction area of 2,000㎡. In May 2012, the project officially started to implement after passing evaluation. Meihekou City Agricultural Development Office appropriated RMB 4,788,439.43 yuan to Meihekou City Xingda Rice Co., Ltd. twice in 2014 respectively. After the site checking, there existed the difference between the price, quantities and model of the equipments actually procured by the IA with those stipulated in the Feasibility Study Report and the construction area for the fresh storage and that for the warehouse were less than those stipulated in the Feasibility Study Report. For example, the actual construction area for the fresh storage was 800.23㎡and that for the warehouse was 1,733.69㎡and only 3color sorting machines with the amount of RMB 366,000 yuan and one polishing machine with the amount of RMB 72,000 yuan were procured but the remaining equipments were not procured.

（3）In Sept. 2010, Liaoyuan Xiaxing Health Industry High Efficiency Biology Co., Ltd. entrusted Jilin Province Green Food Engineering Design Institute to prepare the Feasibility Study Report for Liaoyuan City Xiaxing Black Fungus Safety Production Chain Model Demonstration Project. The total investment of the project was RMB 8 million yuan, of which RMB 5 million yuan from the World Bank loans. The construction contents included newly construction of a low temperature storage (accessory equipments) and procurement of 8 sets of instruments and equipments. In Nov. 2011, the project officially started to implement after passing evaluation. Agricultural Development Office of Liaoyuan City Finance Bureau appropriated RMB 4,783,289.00 yuan to Liaoyuan Xiaxing Health Industry High Efficiency Biology Co., Ltd. twice in March 2013 and Jan. 2014 respectively. After the site checking, there existed the difference between the price, quantities and model of the equipments actually procured by the IA with those stipulated in the Feasibility Study Report. For example, it planned to procure 1 liquid level detection equipment with the amount of RMB 120,000 yuan, one set of vacuum detection equipment with the amount of RMB 460,000 yuan, one set of fully automatic sealing unit with the amount of RMB 1.2 million yuan, one inspection equipment with the amount of RMB 604,000 yuan and a low temperature storage equipment with the amount of RMB 836,000 yuan but actually, one set of automatic filling machine, one set of fully automatic carton packing machine and one bottle unloading stack were procured. The above-mentioned changes in the equipment procurement haven’t been approved by the Jilin Agricultural Commission. According the project approval files, it should include newly construction of a low temperature storage with the construction area of 500㎡and investment of RMB 1.3 million yuan. Actually, a fresh storage has been built by Xiaxing Company before application for the project. According to the needs, the company didn’t implement plan on newly construction of a low temperature storage. The loan proceeds actually have been used for procurement of cryogenic refrigeration equipments and payment to the capital construction projects in the previous years.

（4）In July 2013, Dehui City Xinyuan Grain Processing Co., Ltd. entrusted Jilin Province Light Industry Design Institute to prepare the Feasibility Study Report for Dehui City Xinyuan Rice Safety Production Chain Model Demonstration Project.The total investment of the project was RMB 11,452,900 yuan, of which RMB 5 million yuan from the World Bank loans. The construction contents included newly construction of a finished product storage with the construction area of 1,500 ㎡, 20 silos, hard surface with an area of 4,700 ㎡and rice processing workshop with the construction area of 600㎡. In Nov. 2013, the project officially started to implement after passing evaluation. After the site checking, there existed the difference between the civil woks projects actually procured by the IA with those stipulated in the Feasibility Study Report. 20 silos should be constructed with the diameter of 10 m and the cost of RMB 960,000 yuan but actually, a canopy position has been built with length of 60 m, width of 34 m, the total storage of 10,000 tons and the cost of RMB 980,000 yuan. Although the implementation contents of the above-mentioned industry chain project are the same as those in the plans on changes, the project existed risks that it may fail to realize expected results for it took too long time to implement and the contents of equipment procurement and project construction contents were not in conformity with those stipulated in the Feasibility Study Report. We suggest that Jilin PMO should strictly review the formalities related to changes for the following production chain projects to ensure that the project implementation can meet the requirements in the Feasibility Study Report.

# Text boxes

8

9