中华人民共和国吉林省审计厅

Jilin Provincial Audit Office of the People’s Republic of China

审  计  报  告

Audit Report

吉审外报〔2014〕111号

JILIN AUDIT REPORT〔2014〕NO.111

项目名称：   吉林省世界银行贷款农产品质量安全项目

Project Name:  Jilin Agricultural Product Quality and Safety Project Funded by the World Bank

贷 款 号：    7899－CN

Loan No. :     7899－CN

项目执行单位：吉林省世行贷款农产品质量安全项目领导小组办公室

Project Entity: Management Office under Leading Group for Jilin Agricultural Product Quality and Safety Project Funded by the World Bank

会计年度：          2013

Accounting Year：     2013

目   录

Contents

一、审计师意见	1

I. Auditor’s Opinion	3

财务报表及财务报表附注	6

Ⅱ. Financial Statements and Notes to the Financial Statements	6

（一）资金平衡表	6

i. Balance Sheet	6

（二）项目进度表	7

ii. Summary of Sources and Uses of Funds by Project Component	7

（三）贷款协定执行情况表	9

iii. Statement of Implementation of Loan Agreement	9

（四）指定账户报表	10

iv. Designated Account Statement	10

（五）财务报表附注	11

v. Notes to the Financial Statements	14

三、审计发现的问题及建议	18

III. Audit Findings and Recommendations	20

一、审计师意见

审计师意见

吉林省世行贷款农产品质量安全项目领导小组办公室：

我们审计了吉林省世行贷款农产品质量安全项目2013年12月31日的资金平衡表及至该日同年度的项目进度表、贷款协定执行情况表和指定账户报表等特定目的财务报表及财务报表附注（第6页至第17页）。

（一）项目执行单位及吉林省财政厅对财务报表的责任

编制上述财务报表中的资金平衡表、项目进度表及贷款协定执行情况表是你办的责任，编制指定账户报表是吉林省财政厅的责任，这种责任包括：

1．按照中国的会计准则、会计制度和本项目贷款协定的要求编制项目财务报表，并使其实现公允反映；

2．设计、执行和维护必要的内部控制，以使项目财务报表不存在由于舞弊或错误而导致的重大错报。

（二）审计责任

我们的责任是在执行审计工作的基础上对财务报表发表审计意见。我们按照中国国家审计准则和国际审计准则的规定执行了审计工作，上述准则要求我们遵守审计职业要求，计划和执行审计工作以对项目财务报表是否不存在重大错报获取合理保证。

为获取有关财务报表金额和披露信息的有关证据，我们实施了必要的审计程序。我们运用职业判断选择审计程序，这些程序包括对由于舞弊或错误导致的财务报表重大错报风险的评估。在进行风险评估时，为了设计恰当的审计程序，我们考虑了与财务报表相关的内部控制，但目的并非对内部控制的有效性发表意见。审计工作还包括评价所选用会计政策的恰当性和做出会计估计的合理性，以及评价财务报表的总体列报。

我们相信，我们获取的审计证据是适当的、充分的，为发表审计意见提供了基础。

（三）审计意见

我们认为，第一段所列财务报表在所有重大方面按照中国的会计准则、会计制度和本项目贷款协定的要求编制，公允反映了吉林省世界银行贷款农产品质量安全项目 2013年12月31日的财务状况及至该日同年度的财务收支、项目执行和指定账户收支情况。

（四）其他事项

我们还审查了本期内报送给世界银行的第018号至060号提款申请书及所附资料。我们认为，这些资料均符合贷款协议的要求，可以作为申请提款的依据。

本审计师意见之后，共同构成审计报告的还有两项内容：财务报表及财务报表附注和审计发现的问题及建议。

中华人民共和国吉林省审计厅

二O一四年六月二十七日

地址：中国吉林省长春市亚泰大街6399号

邮政编码：130022

电话：86-0431-85265070

#### 传真：86-0431-85265765

#### I. Auditor’s Opinion

Auditor’s Opinion

To ：Management Office under Leading Group for Jilin Agricultural Product Quality and Safety Project Funded by the World Bank

We have audited the special purpose financial statements (from page 6 to page 17) of Jilin Agricultural Product Quality and Safety Project Funded by the World Bank, which comprise the Balance Sheet as of December 31, 2013, the Summary of Sources and Uses of Funds by Project Component, the Statement of Implementation of Loan Agreement and the Designated Account Statement for the year then ended, and Notes to the Financial Statements.

Project Entity and Jilin Provincial Finance Department's Responsibility for the Financial Statements

The preparation of the Balance Sheet, the Summary of Sources and Uses of Funds by Project Component and the Statement of Implementation of Loan Agreement is the responsibility of your entity, while the preparation of the Special Account Statement is the responsibility of Jilin Provincial Finance Department, which includes:

i. Preparing and fair presenting the accompanying financial statements in accordance with Chinese accounting standards and system, and the requirements of the project loan agreement;

ii. Designing, implementing and maintaining necessary internal control to ensure that the financial statements are free from material misstatement, whether due to fraud or error.

Auditor’s Responsibility

Our responsibility is to express an opinion on these financial statements based on our audit. We conducted our audit in accordance with the Government Auditing Standards of the People’s Republic of China and International Standards on Auditing. Those standards require that we comply with ethical requirements and plan and perform the audit to obtain reasonable assurance about whether the financial statements are free from material misstatement.

An audit involves performing procedures to obtain audit evidence about the amounts and disclosures in the financial statements. The procedures selected depend on the auditor’s judgment, including the assessment of the risks of material misstatement of the financial statements, whether due to fraud or error. In making those risk assessments, the auditor considers internal control relevant to the entities’ preparation and fair presentation of the financial statements in order to design audit procedures that are appropriate in the circumstances, but not for the purpose of expressing an opinion on the effectiveness of the entity’s internal control. An audit also includes evaluating the appropriateness of accounting policies used and the reasonableness of accounting estimates made by management, as well as evaluating the overall presentation of the financial statements.

We believe that the audit evidence we have obtained is appropriate and sufficient to provide a basis for our audit opinion.

Opinion

In our opinion, the financial statements identified in the first paragraph present fairly, in all material respects, financial position of Jilin Agricultural Product Quality and Safety Project Funded by the World Bank as of December 31, 2013, its financial receipts and disbursements, the project implementation and the receipts and disbursements of the Designated account for the year then ended in accordance with Chinese accounting standards and system, and the requirements of the project loan agreement.

Other Matter

We also examined the withdrawal application No.018 to No.060 and the attached documents submitted to the World Bank during the period. In our opinion, those documents comply with the project loan agreement and can serve as basis for loan withdrawal.

The audit report consists of the Auditor’s Opinion and two more parts hereinafter: Financial Statements and Notes to the Financial Statements, Audit Findings and Recommendations.

Jilin Provincial Audit Office of the People’s Republic of China

June 27, 2014

Address: No. 6399,Yatai Street, Changchun City, Jilin Province, P.R. China

Postcode: 130022

Tel.: 86-0431-85265070

Fax: 86-0431-85265065

The English translation is for the convenience of report users; please take the Chinese audit report as the only official version.

二、财务报表及财务报表附注

Ⅱ. Financial Statements and Notes to the Financial Statements

（一）资金平衡表

i. Balance Sheet

资金平衡表

BALANCE SHEET

（二）项目进度表

ii. Summary of Sources and Uses of Funds by Project Component

项目进度表(一)

SUMMARY OF SOURCES AND USES OF FUNDS BY PROJECT COMPONENT Ⅰ

7

项目进度表(二)

SUMMARY OF SOURCES AND USES OF FUNDS BY PROJECT COMPONENT

8

（三）贷款协定执行情况表

iii. Statement of Implementation of Loan Agreement

贷款协定执行情况表

STATEMENT OF IMPLEMENTATION OF LOAN AGREEMENT

9

（四）指定账户报表

iv. Designated Account Statement

指定账户报表

Designated Account Statement

（五）财务报表附注

财务报表附注

1.项目概况

1.1吉林省世行贷款农产品质量安全项目贷款号：7899－CN；《贷款协定》已于2010年7月20日签订。项目总投资为971,990,000.00元人民币（美元与人民币汇率按1：6.8计算），其中利用世行贷款100,000,000.00美元，贷款期限27年（含宽限期8年），执行世界银行浮动利差贷款利率。

1.2项目总体目标：该项目围绕农产品质量安全保障体系，引进并推广农业标准化生产技术规程，加强对农产品的检测和监管，最大程度减少农产品安全风险，提高生产者和消费者的安全生产和消费意识，全面提升吉林省农产品质量安全水平。

1.3子项目分类说明:项目内容包括两大类五个子项目，第一类是公益性建设项目：包括4个子项目：子项目A：农产品质量安全标准农业规程推广;子项目B：农产品质量安全的公共监测;子项目C：农产品质量安全应用研究、培训和宣传；子项目 E：项目管理和监测。第二类是非公益性生产经营项目（含1个子项目D：安全农产品生产链示范模式）。子项目B 为实体工程，其他子项目均不能形成实体工程，是通过宣传、培训、示范、项目管理等手段来提高对农产品生产、加工、销售全过程质量安全的意识。

2.报表编制范围

根据吉林省世行贷款农产品质量安全项目《贷款协定》和《项目协定》，吉林省世行贷款农产品质量安全项目领导小组办公室为本项目执行机构，吉林省债务管理服务中心(简称：省债务中心)为本项目指定账户管理部门。

3.主要会计政策

3.1会计核算年度采用公历年制，即公历每年1月1日至12月31日。

3.2本项目会计核算执行财政部《世界银行贷款项目会计核算办法》（财际字〔2000〕13号文件）和《吉林省世行贷款农产品质量安全项目财务管理与会计核算办法（试行）》（吉财农发〔2010〕893号文件）等制度，以权责发生制作为核算基础，采用借贷复式记账法记账，以人民币为记账本位币。

3.3外币以辅助账核算，年末按照中华人民共和国财政部规定汇率（1美元＝6.0969元人民币）调整外债并核算汇兑损益。

4.报表科目说明

4.1项目支出情况

截止到2013年末，全省项目共计支出146,298,345.29 元，其中子项目A总支出11,427,182.60元，约占该子项目总投资的8.94%；子项目B总支出24,965,610.96元，约占该子项目总投资的5.46%；子项目C总支出26,716,534.38元,约占该子项目总投资的28.32%；子项目D总支出56,648,037.00元，约占该子项目总投资的29.16%；子项目E总支出26,540,980.35元，约占该子项目总投资的27.12%。

4.2货币资金

2013年12月31日货币资金余额为人民币170,901,869.58 元，比上年增加人民币29,645,941.88元。

4.3预付及应收款

2013年12月31日余额为人民币4,477,269.54元，主要是2013年吉林省世行项目办统一采购项目采样车辆按合同支付给供货商（中国航天科工集团华东物资代销站）的采购预付款。

4.4项目拨款

截止到2013年末，全省项目办账户国内配套资金共计到位198,833,164.82 元。

4.5世行贷款

截止到2013年末，全省项目办共计提取世行贷款19,126,830.92美元（含世行直接支付）;周转金账户设在外债中心。

4.6应付款

2013年12月31日余额为人民币4,377,098.96元，主要是吉林省邮电规划设计院有限公司质量保证金、惠诺德（北京）科技有限公司履约保证金、清华同方公司的履约保证金，以及吉林省世行项目办统一采购的超低温冰箱未支付给供应商的采购款。

4.7留成收入

2013年12月31日余额人民币1,852,845.19元，主要是银行存款利息收入。

5.其他说明事项

对不能形成实体工程的子项目（如：子项目A、子项目C和子项目E全部属于支出费用），我们选用了“其他投资”“待摊投资”，按照子项目分别归集支出核算投资成本，待项目建设期结束时分五个子项目进行决算。另外，对该项目银行存款产生的利息收入，选用“留成收入”进行核算。

v. Notes to the Financial Statements

Notes to Financial Statements

1. Project overview

1.1 Loan No. 7899－CN of Jilin Provincial Agricultural Product Quality and Safety Project Funded by the World Bank: the Loan Agreement was signed on July 20, 2010. The total investment of the project is RMB 971,990,000.00 yuan (exchange rate of USD and RMB: 1: 6.8), including the World Bank loan of USD100,000,000.00, loan period: 27 years (including the grace period of 8 years), the floating spread loan interest rate of the World Bank is executed.

1.2 Overall objective of the project: The project focuses on the agricultural product quality and safety support system to introduce and popularize the agricultural standard production technical specification, strengthen the testing and supervision of agricultural products, reduce the safety risks of agricultural products, to the greatest extent, improve the safe production and awareness of consumption of the producers and consumers and improve the agricultural product quality and safety level of Jilin Province in an all-round way.

1.3 Classification description of sub-components: The project includes 5 sub-components in 2 categories. The first category includes the public welfare sub-components, that is, 4 sub-components: sub-component A: Agricultural Product Quality and Safety Standard Agricultural Specification Popularization; sub-component B: Agricultural Product Quality and Safety Public Monitoring; sub-component C: Agricultural Product Quality and Safety Application Research, Training and Publicity; sub-component E: Project Management and Monitoring. The second category includes 1 public welfare production and operation sub-component (sub-component D: Safe Agricultural Products Production Chain Demonstration Model). The sub-component B is the physical works and all the other sub-components cannot construct the physical works and they are used to improve the awareness of quality safety in the whole process of production, processing and sales of agricultural products by means of publicity, training, demonstration and project management, etc.

2. Consolidation Scope of the Financial Statements

According to the Loan Agreement and the Project Agreement of Jilin Provincial Agricultural Product Quality and Safety Project Funded by the World Bank, the Office of the Leading Group of Jilin Provincial Agricultural Product Quality and Safety Project is the Executing Agency of the project and Jilin Provincial Debt and Adminstration and Service Center (hereinafter referred to as the Provincial Debt Center) is the special account management department of the project.

3. Accounting Policies

3.1 The fiscal year takes the Gregorian calendar, that is, January 1-December 31.

3.2 Some systems such as Accounting Measures of the World Bank Loan Projects (CJZi [2000] No. 13 Document) of the Ministry of Finance and the Financial Management and Accounting Measures of Jilin Provincial Agricultural Product Quality and Safety Project Funded by the World Bank (Provisional) (JCNF [2010] No. 893 Document), etc. are implemented for the accounting of the project.The accounting is on the accrual basis.The double entry bookkeeping of debit and credit is taken and RMB is taken as the recording currency.

3.3 The foreign currency is used for accounting of the auxiliary accounts and the foreign debts are adjusted and the accounting of the exchange gain or loss is made according to the exchange rate (USD 1= RMB 6.0969 yuan) stipulated by the Ministry of Finance of the People’s Republic of China.

4. Explanation of Subjects

4.1 Total Project expenditures

By the end of 2013, the total expenditure of the sub-components in the whole province was RMB 146,289,345.29 yuan, of which RMB 11,427,182.60 yuan for sub-component A, accounting for about 8.94% of the total investment of the sub-component A; RMB 24,965,610.96 yuan for sub-component B, accounting for about 5.46% of the total investment of the sub-component B; RMB 26,716,534.38 yuan for sub-component C, accounting for about 28.32% of the total investment of the sub-component C; RMB 56,684,037.00 yuan for sub-component D, accounting for about 29.16% of the total investment of the sub-component D; RMB 26,540,980.35 yuan for sub-component E, accounting for about 27.12% of the total investment of the sub-component E.

4.2 Cash and Bank

The balance of the monetary funds was RMB 170,901,869.58 yuan by December 31, 2013, which rose by RMB 29,645,941.88 yuan from last year.

4.3 Prepaid and Receivable

The balance was RMB 4,477,269.54 yuan by December 31, 2013, mainly the advance payments for purchasing the Sampling vehicles in the uniform purchase sub-component of Jilin Provincial World Bank Project Office to the supplier (Chinese Aerospace Science and Industry Group East China material consignment Station) in 2013.

4.4 Project Appropriation Funds

By the end of 2013, the total domestic counterpart funds of the account of the whole Provincial Project Office in place was RMB 198,833,164.82 yuan.

4.5 World Bank loan

By the end of 2013, the whole Provincial Project Office has withdrawn from the World Bank loan of USD 19,126,830.92 (including those directly paid by the World Bank); the imprest account is set in the Debt Center.

4.6 payable

By December 31, 2013, the balance was RMB 4,377,098.96 yuan, mainly the bind bonds of Jilin Provincial Post and Telecommunications Design Institute Co., Ltd.，HuiNuode (Beijing) Technology Co., Ltd.  and Qinghua Tongfang Co., Ltd. and the money for the uniform purchase of Ultra low temperature freezer of Jilin Provincial World Bank Project Office unpaid to the suppliers.

4.7 Retained earnings

By December 31, 2013, the balance was RMB 1,852,845.19 yuan, mainly the bank deposits and interest income.

5. Other Explanation for the Financial Statements

For some sub-components which will not construct the physical works (such as sub-component A, sub-component C and sub-component E, all of which belong to the scope of expenditure), we have chosen “other investment” and “investment to be amortized” to collect the expenditure and make accounting of the investment cost according to the sub-components, respectively and carry out final accounting of the 5 sub-components when the project construction period is ended. In addition, we have chosen “retained earnings” for accounting of the interest income produced by the bank deposits of the project.

三、审计发现的问题及建议

审计发现的问题及建议

除对财务报表进行审计并发表审计意见外，审计中我们还关注了项目执行过程中相关单位国家法规和项目贷款协定遵守情况、内部控制和项目管理情况、项目绩效及上年度审计建议整改落实情况。我们发现存在如下问题：

（一）聘请社会中介机构进行项目咨询未出具咨询报告

2011年11月，省世行贷款农产品质量安全项目办委托省建设项目招标有限责任公司，对项目财务咨询进行招标，大华会计师事务所（原吉林招贤求实会计师事务有限公司）以1,950,000.00元中标并签订审计与财务咨询业务约定书，服务期5年（2011年12月-2016年10月）。2013年6月至2013年2月，大华会计师事务所对省世行贷款农产品质量安全项目81个单位提供了审计与财务咨询服务，未出具咨询报告。2013年6月4日，省世行贷款农产品质量安全项目办按工作进度向大华会计师事务所支付财务咨询审计费140,000.00元。建议你办协调会计师事务所出具相关咨询报告。你办已接受审计建议。

（二）省项目办财政资金余额较大，资金使用率不高

截至2013年12月末，依据每年的预算安排，省财政厅向省世行贷款农产品质量安全项目办拨付财政配套资金和项目管理专项经费101,134,400.00元，省世行贷款农产品质量安全项目办已支出和拨付各项目办资金16,489,439.20元，2013年年末余额84,644,960.80元。省世行贷款农产品质量安全项目办银行存款最小为8月末余额57,314,176.07元，最大为12月末余额84,644,960.80元，全年平均月末余额66,908,939.30元，滞留在账户中，余额较大，未能充分发挥财政资金的使用效益，资金使用率不高。

（三）项目进度过慢

2009年12月，吉林省发改委下发《关于吉林省世行贷款农产品质量安全项目可行性研究报告的批复》（吉发改审批〔2009〕1085号），项目建设期限5年（2010年-2015年），项目总投资971,990,000.00元，利用世行贷款100,000,000.00美元，地方配套资金291,990,000.00元，2010年10月，项目正式启动。至2013年12月末，该项目累计完成投资146,298,345.29元，占项目总投资的15.05%，项目实施进度过慢。

对问题（二）（三），建议你办督促各项目单位尽快实施相关项目建设，保证项目按计划实施，充分发挥资金的使用效益。你办已接受审计建议。

（四）上一年度审计发现问题未整改情况

2013年审计报告中披露的问题中，除项目进度过慢的问题仍然存在外，其他问题已得到落实整改。

III. Audit Findings and Recommendations

Audit Findings and Recommendations

In addition to performing the audit and expressing an opinion on the financial statements, we also make observations with respect to compliance with applicable provisions of state laws and regulations and the loan agreement of the relevant entities, its internal financial control and project management, project performance and the follow-up of previous recommendations during the project implementing process. We found the following issues:

（Ⅰ）The public intermediary agent was recruited to provide the consultation for the project but it didn’t provide the consultation report.

In Nov. 2011, the Management Office under Leading Group for Jilin Agricultural Product Quality and Safety Project Funded by the World Bank (Jilin PMO) entrusted Jilin Province Construction Project Bidding Co., Ltd. to invite bids for the financial consultation of the project. Dahua Accounting Firm (former Jilin Zhaoxian Qiushi Accounting Co., Ltd.) won the bid with the contract price of RMB 1,950,000.00 yuan. Both parties signed an Audit and Financial Consultation Agreement with the service term of five years (Dec. 2011 to Oct. 2016). From June 2013 to Feb. 2013, Dahua Accounting Firm provided 81 units under the Project with the audit and financial consultation services without issuance of the consultation report. On June 4, 2013, the Jilin PMO paid the expenses for the audit and financial consultation of RMB 140,000.00 yuan to Dahua Accounting Firm according to the work schedule. We suggest that your PMO should coordinate the Accounting Firm to issue the consultation report. Your PMO has accepted the audit recommendation.

（Ⅱ）Jilin PMO has considerable balance of the fiscal funds with low utilization rate

By the end of Dec. 2013, according to the annual budget arrangement, Jilin Province Finance Bureau has appropriated the financial counterpart funds and special funds for project management of RMB 101,134,400.00 yuan and Jilin PMO has disbursed and appropriated the funds of RMB 16,489,439.20 yuan. In the end of 2013, its balance was RMB 84,644,960.80 yuan. For the bank deposit, it recorded that the minimum balance was RMB 57,314,176.07 yuan as of August and the maximum balance was RMB 84,644,960.80 yuan as of Dec. The average remaining balance was RMB 66,908,939.30 yuan in a year. The considerable balance was stranded in the account, which didn’t fully improve the funding returns with the low utilization rate.

（Ⅲ）Too slow project progress

In Dec. 2009, Jilin DRC approved the Feasibility Study Report for Jilin Agricultural Product Quality and Safety Project（JFGSP〔2009〕No.1085） with the construction period of five years （2010 -2015） and the total investment of RMB 971,990,000.00 yuan. The World Bank loan was USD 100,000,000.00 and the local counterpart funds were RMB 291,990,000.00 yuan. In Oct. 2010, it formally started. By Dec. 2013, it has completed the accumulative total investment of RMB 146,298,345.29 yuan, which accounted for 15.05% of the total investment. The project was too slow.

For the issue (Ⅰ) and issue (Ⅱ), we suggest that your PMO should urge the IAs to implement the relevant projects as early as possible and ensure that the projects can be implemented as planned and fully improve the funding returns. Your PMO has accepted the audit recommendation.

(Ⅳ)The Followed-up of previous recommendations

According to the audit, among those disclosed in the audit report in 2013, except for too slow project progress, the other issues have been rectified.