中华人民共和国吉林省审计厅

Jilin Provincial Audit Office of the People’s Republic of China

审  计  报  告

Audit Report

吉审外报〔2014〕110号

JILIN AUDIT REPORT〔2014〕NO.110

项目名称：   亚洲开发银行贷款吉林松花江水污染治理项目

Project Name: Jilin Songhua River Basin Water Pollution Control and Management Project Financed by the Asian Development Bank

贷 款 号：    2487-PRC

Loan No. :     2487-PRC

项目执行单位：吉林省亚洲开发银行贷款松花江流域水污染防治项目领导小组办公室

Project Entity:  Management Office under Leading Group for Jilin ADB-financed Songhua River Basin Water Pollution Control and Management Project

会计年度：     2013

Accounting Year：2013

目   录

Contents

一、审计师意见	1

I. Auditor’s Opinion	3

二、财务报表及财务报表附注	6

Ⅱ. Financial Statements and Notes to the Financial Statements	6

（一）资金平衡表	6

i. Balance Sheet	6

（二）项目进度表	7

ii. Summary of Sources and Uses of Funds by Project Component	7

（三）贷款协定执行情况表	9

iii. Statement of Implementation of Loan Agreement	9

（四）专用账户报表	10

iv. Special Account Statement	10

（五）财务报表附注	11

v. Notes to the Financial Statements	14

三、审计发现的问题及建议	17

III. Audit Findings and Recommendations	28

一、审计师意见

审计师意见

吉林省亚洲开发银行贷款松花江流域水污染防治理项目领导小组办公室：

我们审计了亚洲开发银行贷款松花江流域水污染防治理项目2013年12月31日的资金平衡表及截至该日同年度的项目进度表、贷款协定执行情况表和专用账户报表等特定目的财务报表及财务报表附注(第6页至第16页)。

（一）项目执行单位及吉林省财政厅对财务报表的责任

编制上述财务报表中的资金平衡表、项目进度表及贷款协定执行情况表是你办的责任，编制专用账户报表是吉林省财政厅的责任，这种责任包括：

1．按照中国的会计准则、会计制度和本项目贷款协定的要求编制项目财务报表，并使其实现公允反映；

2．设计、执行和维护必要的内部控制，以使项目财务报表不存在由于舞弊或错误而导致的重大错报。

（二）审计责任

我们的责任是在执行审计工作的基础上对财务报表发表审计意见。我们按照中国国家审计准则和国际审计准则的规定执行了审计工作，上述准则要求我们遵守审计职业要求，计划和执行审计工作以对项目财务报表是否不存在重大错报获取合理保证。

为获取有关财务报表金额和披露信息的有关证据，我们实施了必要的审计程序。我们运用职业判断选择审计程序，这些程序包括对由于舞弊或错误导致的财务报表重大错报风险的评估。在进行风险评估时，为了设计恰当的审计程序，我们考虑了与财务报表相关的内部控制，但目的并非对内部控制的有效性发表意见。审计工作还包括评价所选用会计政策的恰当性和作出会计估计的合理性，以及评价财务报表的总体列报。

我们相信，我们获取的审计证据是适当的、充分的，为发表审计意见提供了基础。

（三）审计意见

我们认为，第一段所列财务报表在所有重大方面按照中国的会计准则、会计制度和本项目贷款协定的要求编制，公允反映了亚洲开发银行贷款松花江流域水污染防治理项目 2013年12月31日的财务状况及截至该日同年度的财务收支、项目执行和专用账户收支情况。

（四）其他事项

我们还审查了本期内报送给亚洲开发银行的B-J0092至B-J0115提款申请书及所附资料。我们认为，这些资料均符合贷款协议的要求，可以作为申请提款的依据。

本审计师意见之后，共同构成审计报告的还有两项内容：财务报表及财务报表附注和审计发现的问题及建议。

中华人民共和国吉林省审计厅

二○一四年六月二十七日

地址：中国吉林省长春市亚泰大街6399号

邮政编码：130022

电话：86-0431-85265070

传真：86-0431-85265765

#### I. Auditor’s Opinion

Auditor’s Opinion

To Management Office under Leading Group for Jilin ADB-financed Songhua River Basin Water Pollution Control and Management Project

We have audited the special purpose financial statements (from page 6 to page 16) of Jilin Songhua River Basin Water Pollution Control and Management Project Financed by the Asian Development Bank, which comprise the Balance Sheet as of December 31, 2013, the Summary of Sources and Uses of Funds by Project Component, the Statement of Implementation of Loan Agreement and the Special Account Statement for the year then ended, and Notes to the Financial Statements.

Project Entity and Jilin Provincial Finance Department's Responsibility for the Financial Statements

The preparation of the Balance Sheet, the Summary of Sources and Uses of Funds by Project Component and the Statement of Implementation of Loan Agreement is the responsibility of your entity, while the preparation of the Special Account Statement is the responsibility of Jilin Provincial Finance Department, which includes:

i. Preparing and fair presenting the accompanying financial statements in accordance with Chinese accounting standards and system, and the requirements of the project loan agreement;

ii. Designing, implementing and maintaining necessary internal control to ensure that the financial statements are free from material misstatement, whether due to fraud or error.

Auditor’s Responsibility

Our responsibility is to express an opinion on these financial statements based on our audit. We conducted our audit in accordance with the Government Auditing Standards of the People’s Republic of China and International Standards on Auditing. Those standards require that we comply with ethical requirements and plan and perform the audit to obtain reasonable assurance about whether the financial statements are free from material misstatement.

An audit involves performing procedures to obtain audit evidence about the amounts and disclosures in the financial statements. The procedures selected depend on the auditor’s judgment, including the assessment of the risks of material misstatement of the financial statements, whether due to fraud or error. In making those risk assessments, the auditor considers internal control relevant to the entity’s preparation and fair presentation of the financial statements in order to design audit procedures that are appropriate in the circumstances, but not for the purpose of expressing an opinion on the effectiveness of the entity’s internal control. An audit also includes evaluating the appropriateness of accounting policies used and the reasonableness of accounting estimates made by management, as well as evaluating the overall presentation of the financial statements.

We believe that the audit evidence we have obtained is appropriate and sufficient to provide a basis for our audit opinion.

Opinion

In our opinion, the financial statements identified in the first paragraph present fairly, in all material respects, financial position of Jilin Songhua River Basin Water Pollution Control and Management Project Financed by the Asian Development Bank as of December 31, 2013, its financial receipts and disbursements, the project implementation and the receipts and disbursements of the special account for the year then ended in accordance with Chinese accounting standards and system, and the requirements of the project loan agreement.

Other Matter

We also examined the withdrawal application from B-J0092 to B-J0115 and the attached documents submitted to the Asian Development Bank during the period. In our opinion, those documents comply with the project loan agreement and can serve as basis for loan withdrawal.

The audit report consists of the Auditor’s Opinion and two more parts hereinafter: Financial Statements and Notes to the Financial Statements, Audit Findings and Recommendations.

Jilin Provincial Audit Office of the People’s Republic of China

June 27, 2014

Address: No. 6399,Yatai Street,ChangChunCity, Jilin Province, P.R. China

Postcode: 130022

Tel.: 86-0431-85265070

Fax: 86-0431-85265765

The English translation is for the convenience of report users; Please take the Chinese audit report as the only official version.

二、财务报表及财务报表附注

Ⅱ. Financial Statements and Notes to the Financial Statements

（一）资金平衡表

i. Balance Sheet

资 金 平 衡 表

BALANCE SHEET

（二）项目进度表

ii. Summary of Sources and Uses of Funds by Project Component

项 目 进 度 表（一）

SUMMARY OF SOURCES AND USES OF FUNDS

BY PROJECT COMPONENT Ⅰ

本期截至2013年12月31日 	(For the period ended December 31, 2013）

项 目 进 度 表（二）

SUMMARY OF SOURCES AND USES OF FUNDS

BY PROJECT COMPONENT Ⅱ

本期截至2013年12月31日 (For the period ended December 31, 2013）

8

（三）贷款协定执行情况表

iii. Statement of Implementation of Loan Agreement

贷 款 协 定 执 行 情 况 表

STATEMENT OF IMPLEMENTATION OF LOAN AGREEMENT

本期截至2013年12月31日 (For the period ended December 31, 2013）

9

（四）专用账户报表

iv. Special Account Statement

专 用 账 户 报 表

SPECIAL ACCOUNT STATEMENT

本期截至2013年12月31日(For the period ended December 31, 2013）

（五）财务报表附注

财务报表附注

1.项目概况

根据亚行贷款松花江流域水污染控制和管理《贷款协定》和《转贷协定》，本项目贷款在2008年12月批准，项目的实施从2009年1月开始。项目贷款编号2487-PRC，《贷款协议》已于2009年5月5日签订，工程总投资1,482,710,000.00元人民币。其中：利用亚行贷款100,000,000.00美元。本项目的目标是减少污染以及改善松花江流域水资源管理与利用。

2. 财务报表编制范围

项目主要由9家污水处理厂，10家垃圾处理厂，及长白山综合治理项目单位组成。本报表由20个子项目报表和吉林省债务管理服务中心项目报表汇总编制。

3. 主要会计政策

3.1本项目财务报表按照财政部《世界银行贷款项目会计核算办法》（财际字〔2000〕13号）的要求编制。

3.2会计核算年度采用公历年制，即公历每年1月1日至12月31日。

3.3本项目会计核算以 “权责发生制”作为记账原则，采用借贷复式记账法记账，以人民币为记账本位币。

3.4 按照中国人民银行2013年12月30日汇率，即USD1=人民币6.0969元。

4.报表科目说明

4.1项目支出

2013年项目支出人民币166,538,359.12元，累计支出人民币1,373,817,147.45元，占总投资计划的92.66%。

4.2货币资金

2013年12月31日货币资金余额为人民币69,309,544.48元，比上年减少人民币20,083,397.14元，其中专用账户存款折合人民币431,626.13元。

4.3预付及应收款

2013年12月31日余额为人民币241,170,913.00元。

4.4项目拨款

2013年12月31日余额为人民币950,348,641.88元，是中央、省、市、各级到位的配套资金。

项目计划配套资金总额人民币820,440,237.00元，截至2013年12月31日到位配套人民币1,051,162,199.88元，占计划的128.12%，其中：中央计划配套资金总额人民币211,163,680.00元，累计到位人民币334,240,051.82元，占计划的158.28%；省级计划配套资金总额人民币339,866,900.00元，累计到位人民币273,469,133.31元，占计划的80.46%；市级计划配套资金总额人民币159,982,457.00元，累计到位人民币303,854,592.56元，占计划的189.93%。

4.5项目借款

2013年12月31日余额为人民币557,117,570.68元，其中：亚行开发银行贷款额为85,093,082.17美元，折合人民币518,804,012.68元。

截至2013年12月31日，累计提取亚行开发银行贷款资金85,093,082.17美元，占贷款总额的85.09%。其中：工程类累计提款41,742,050.89美元，占该类计划的99.70%;货物类累计提款41,455,326.14美元，占该类计划的83.69%；培训类累计提款0美元，占该类计划的0%；咨询服务类累计提款685,913.56美元，占该类计划的57.16%。

4.6应付款

2013年12月31日余额为人民币113,881,684.42元。

4.7留成收入

2013年12月31日余额人民币28,590.01元，主要是银行存款利息收入。

5.专用账户使用情况

本项目专用账户设在建设银行长春西安大路支行，账号为 22014007500229200744，币种为美元。专用账户首次存款 3,000,000.00美元。2013年年初余额234,315.19美元，本年度回补0美元，利息收入115.17美元，本年度支付163,636.00美元，年末余额70,794.36美元。

6.其他需要说明的事项

项目资金平衡表中亚洲开发银行贷款期末数与期初数之差、项目进度表中相应本期发生额与贷款协定执行情况表人民币本期提款数不一致是由于历年汇兑损益造成的。

## v. Notes to the Financial Statements

Notes to the Financial Statements

1. Project overview

According to Loan Agreement and Project Agreement of ADB Financed Songhua River Basin Water Pollution Control and Management Project, the loan was approved in December, 2008. Implementation was started in January, 2009. Loan NO.:2487-PRC.The Loan Agreement was signed on May 5,2009,total investment is RMB1,482,710,000.00yuan which includes USD100,000,000.00 of ADB loan.Aim of the project is reduce pollution and improve management/utilization of Songhua River Basin.

2. Consolidation Scope of the Financial Statements

The project includes 9 wastewater treatment plants, 10 solid waste managements and a Changbaishan Integrated River Improvement. The statement is prepared with information from 20 subprojects and the Project Summary Sheet provided by Jilin Province Debt Management Service Center.

3. Accounting Policies

3.1 The Financial Statements of the project were prepared according to the requirements of Accounting Methods for the World Bank Financed Project（Caijizi[2000]No.13）.

3.2 In accounting practice, the Gregorian calendar year is adopted as the fiscal year from January 1 to December 31.

3.3 The accrual basis and the debit/credit double entry bookkeeping method are adopted. RMB is used as the recording currency of bookkeeping.

3.4 The exchange rate adopted in the financial statements was the exchange rate on December 31, 2013 of the People’s Bank of China, which is USD1= RMB6.0969yuan.

4. Explanation of Subjects

4.1 Total Project expenditures

The project expenditure in 2013was RMB166,538,359.12yuan, and the cumulative expenditures were RMB1,373,817,147.45yuan, which accounted for 92.66% of the total investment plan.

4.2 Cash and Bank

On December 31, 2013, the balance was RMB69,309,544.48yuan with a decrease of RMB20,083,397.14yuan compared with that of the last year. And the funds in the Special Account were converted to RMB431,626.13yuan.

4.3 Prepaid and Receivable

Its balance on December 31, 2013 was RMB241,170,913.00 yuan.

4.4 Project Appropriation Funds

The balance on December 31, 2013 was RMB950,348,641.88yuan, which was the counterpart funds allocated by all levels including the central authorities,the province, the city.

The total planned counterpart funds of this project were RMB820,440,237.00yuan. By the end of 2013, RMB1,051,162,199.88yuan of the counterpart funds had been allocated, which accounted for 128.12% of the plan. among which: The total planned counterpart funds for the center level were RMB211,163,680.00yuan and the actual cumulative allocated funds were RMB334,240,051.82yuan, 158.28% of the plan; The total planned counterpart funds for the province level were RMB339,866,900.00yuan and the actual cumulative allocated funds were RMB273,469,133.31yuan, 80.46% of the plan; The total planned counterpart funds for the city level were RMB159,982,457.00yuan and the actual cumulative allocated funds were RMB303,854,592.56yuan189.93% of the plan.

4.5 Project Loan

The balance on December 31, 2013 was RMB557,117,570.68yuan, including the ADB loan USD85,093,082.17 equivalent to RMB518,804,012.68yuan.

By the end of December 31, 2013, accumulated USD85,093,082.17of the ADB loan had been withdrawn, accounting for 85.09% of the total, among which the withdrawal for civil works was USD41,742,050.89,  accounting for99.70% of the category plan; the withdrawal for goods was USD41,455,326.14, accounting for 83.69% of the category plan; the withdrawal for training was USD0, accounting for 0% of the category plan; the withdrawal for consulting services was USD685,913.56, accounting for 57.16%of the category plan.

4.6 Payable

The balance on December 31, 2013 was RMB113,881,684.42yuan.

4.7 Retained Earnings

The balance on December 31, 2013 was RMB28,590.01yuan, mainly interest earned of bank deposit.

5. Special Account

The Special Account of this project is set in Construction Bank,ChangChun Xi’an Road Branch, with the account number of 22014007500229200744, and USD as currency Unit. The initial Deposit of the Special Account is USD3,000,000.00. The beginning balance of 2013 was USD234,315.19. This year USD0 has been replenished and the interest earned was USD115.17. In 2013 fiscal year, USD163,636.00 has been paid. Thus, the ending balance was USD70,794.36.

6. Other Explanation for the Financial Statements

Due to the change of foreign exchange rate, there are discrepancies between the difference of the beginning and ending balance of the ADB loan in the Balance Sheet, the cur	rent year’s loan received in the Summary of Sources and Uses of Funds by Project Component and the amount of current year’s withdrawals (disclosed in RMB) in the Statement of Implementation of Loan Agreement.

三、审计发现的问题及建议

审计发现的问题及建议

除对财务报表进行审计并发表审计意见外，审计中我们还关注了项目执行过程中相关单位国家法规和项目贷款协定遵守情况、内部控制和项目管理情况、项目绩效及上年度审计建议整改落实情况。我们发现存在如下问题：

（一）违反国家法规或贷款协定的问题

1．部分项目超概算20,954,874.17元

至2014年5月，靖宇县污水处理项目等4个项目中的部分工程超概算20,954,874.17元，其中长白山管委会松花江流域上游（白溪 东岗 漫江）水污染综合治理道路项目工程三号街、三号路、四号街、四号路道路工程超概算2,768,300.00元，辉南县垃圾处理项目车辆超概算3,539,535.00元，靖宇县污水处理项目单位管理费超概算681,939.17元，公主岭范家屯镇污水处理工程项目建安工程和设备安装采购超概算13,965,100.00元。

不符合《关于改进工程建设概预算工作的若干规定》（计标〔1983〕1038号）第十一条“各有关部门和有关单位都应认真执行批准的总概算，不得任意突破”的规定。建议你办督促相关项目单位向原概算批复部门申请调整概算。你办已接受审计建议。2014年6月,靖宇县污水处理项目单位管理费超概算问题已整改。

2．工程未招标先施工

2010年7月，靖宇县政府为使靖宇县污水处理项目在当年建成通水，靖宇县政府经过县长办公会研究，决定由泸州市第七建筑工程公司靖宇分公司（简称泸州七建）对污水项目的土建和管网工程先行开工建设。2010年11月，在招标过程中泸州七建没有中标，由中标单位吉林星泰公司接管施工。至2012年初，已拨付泸州七建工程款52,900,000.00元，已开发票8,000,000.00元，其余44,900,000.00元未取得发票，在预付工程款挂账，影响项目的建安投资44,900,000.00元。

不符合《中华人民共和国招标投标法》第三条“在中华人民共和国境内进行下列工程建设项目包括项目的勘察、设计、施工、监理以及与工程建设有关的重要设备、材料等的采购，必须进行招标：（一）大型基础设施、公用事业等关系社会公共利益、公众安全的项目；（二）全部或者部分使用国有资金投资或者国家融资的项目；（三）使用国际组织或者外国政府贷款、援助资金的项目”的规定。建议你办督促项目单位严格执行招投标法的规定，杜绝此类问题的发生。你办已接受审计建议。

3．挪用项目建设资金支付临时工工资、公益岗位人员工资380,996.00元

2011年至2014年，靖宇县污水处理项目在待摊投资中列支各项人员工资380,996.00元，其中支付临时工工资230,996.00元，支付公益岗位人员工资150,000.00元，形成挪用项目建设资金支付临时工工资230,996.00元、公益岗位人员工资150,000.00元。

不符合财政部《国际金融组织和外国政府贷款赠款管理办法》（2006年财政部第38号令）第二十八条“贷款资金的使用应当符合贷款法律文件的规定，……不得以任何理由和形式滞留、截留、挪用贷款资金或者擅自改变贷款资金用途”的规定。建议你办督促相关项目单位归还项目建设资金。你办已接受审计建议。2014年6月，靖宇县政府已配套资金380,996.00元补齐挪用的专款。

4．未按概算要求购置车辆，多支付车辆款78,100.00元，多支付培训费10,000.00元

2010年12月，靖宇县污水处理项目车辆采购通过公开招投标确定中标单位为黑龙江省华澄环保节能工程有限责任公司，合同价1,986,620.00元，至2014月4月，亚行已直接支付黑龙江华澄公司全部车辆款，按合同规定应采购工作用车一辆385,000.00元，水质检测车一辆295,800.00元，实际未采购，合计680,800.00元，实际采购车辆为本田CRV2.4 一辆239,800.00元，别克商务车一辆322,900.00元，五菱面包车一辆40,000.00元，合计金额602,700.00元，形成未按概算要求购置车辆，多支付车辆款78,100.00元。合同中规定的车辆款包含培训费10,000.00元，在合同执行过程中，黑龙江华澄公司未提供相应的培训，多支付培训费10,000.00元。

不符合靖宇县污水处理工程项目车辆采购《合同》和《建设项目审计处理暂行规定》第十四条“工程价款结算中多计少计的工程款应予调整”的规定。建议你办监督项目单位按合同采购车辆，收回多支付车辆价款。你办已接受审计建议。2014年6月,供货商已退还多支付车辆款78,100.00元。

5．多支付设备款30,000.00元

2010年6月,辉南县垃圾处理项目通过公开招投标采购日处理渗滤液设备一套,中标人为北京天地人环保科技有限公司，截至审计日,项目单位按合同已全部支付设备款4,340,100.00元，其中包含国内考察费30,000.00元，因北京天地人环保科技有限公司未提供国内考察服务，所以该项目多支付设备款30,000.00元。

不符合辉南县垃圾处理项目设备采购《合同》和《建设项目审计处理暂行规定》第十四条“工程价款结算中多计少计的工程款应予调整”的规定。建议你办监督项目单位收回多支付设备款。你办已接受审计建议。

6．中标商未严格执行采购合同，扶余县污水公司原车队队长等人参与车辆采购，实际采购的车辆与合同中参数不符，主要参数降低

（1）2010年6月29日和2010年12月23日，扶余县污水处理项目的车辆采购在未收到车辆的情况下，经扶余县污水公司原经理刘彦辉签字同意，违规预付车辆采购中标商--中经东源公司购车款920,000.00元和100,000.00元，合计1,020,000.00元（合同中规定，收到中标商提供的形式发票，预付30%货款；收到全部货物并验收合格后支付70%货款）。中标商未执行采购合同，将车辆采购交由污水公司原车队队长盛小明负责。据盛小明证实，中经东源公司代表蔡铭联系他本人购买车辆,并和扶余县三岔河瑞麟汽车修配厂签订采购合同（和原中标合同车辆参数一致），合同价款920,000.00元，实际是由盛小明采购（采购车辆的事情刘彦辉经理也知道）。2010年7月12日，中东经源公司将920,000.00元购车款转入扶余县三岔河瑞麟汽车修配厂，并于2010年7月26日将全部资金转入盛小明个人卡中（中国农业银行扶余站前支行，卡号6228483730135573813），2010年7月27日至2012年12月21日盛小明将卡中款项全部支出（至2013年6月25日卡中无余额），主要用于购买5台车辆，分别为一汽解放自卸汽车1辆、二手瑞沃自卸汽车1辆、郑州宇通客车1辆、丰田汉兰达汽车1辆、叉车1辆及办理相关手续等，上述购买车辆除丰田汉兰达汽车外，实际采购车辆与合同中参数不符，主要参数降低。其中，盛小明购买的二手瑞沃自卸汽车，系经扶余县住建局原局长刘长文和扶余县污水公司原经理刘彦辉同意，由盛小明经手购买了扶余县住建局会计孟瑰丽的亲属王继业、孙振雨共同所有的一台旧瑞沃140型自卸汽车，用于抵顶车辆采购合同中应购买的1辆一汽解放自卸汽车（合同价款167,900.00元），据盛小明和王继业证实，该二手车定价100,000.00元，由盛小明以现金支付给王继业。该二手车交易无收据，无合同，卖方未提供发票，至2014年5月尚未过户，该车现停放在扶余县污水公司院内。扶余县污水公司原经理刘彦辉证实，该车曾用于污水公司拉过工程用土方、污泥等。扶余县污水公司现负责人吴君证实，该车自其2012年7月到任后无法启动，未曾使用过。

（2）2010年9月29日，扶余县污水公司铲车采购中标商中国重型机械总公司未履行采购职责，将铲车的采购交给盛小明负责，并将购车款297,105.00元转入扶余县三岔河鑫兴五金商店，盛小明将此款全部提现，并去松原市购买1辆铲车,但主要参数比合同中主要参数降低。据盛小明证实，扶余县污水公司工艺设备采购合同中的1辆铲车是由中标方——中国重型机械总公司代表蔡铭联系他本人购买。

据盛小明证实，除二手瑞沃自卸汽车外，其他车辆在购车时取得了发票，现在以找不到为由无法提供当时购车发票。扶余县污水公司与中标商购车的合同价款为1,310,000.00元，对扶余污水公司由盛小明实际采购的车辆，审计组按网上询价最低价为873,800.00元，最高价为1,006,600.00元，因实际购车参数与合同中车辆参数不符可能形成的最低和最高差价为303,400.00元和436,200.00元（具体金额因审计手段有限，无法查明），涉嫌造成国有资产损失或相关工作人员骗取国有资金的行为。

扶余县污水公司由盛小明经手购买的6台车辆，无收货单及验收证明，中标方仅提供形式发票，未按我国税法规定提供正规发票，因无正规发票，现上述车辆购车款均在扶余污水公司预付工程款中挂账，车辆也未做资产管理。经实际盘点及相关人员证实，一汽解放自卸车、铲车、宇通客车、叉车能正常使用，汉兰达轿车因污水公司经济纠纷被扶余市法院查封，二手瑞沃自卸汽车现为卖方车籍，双方未过户，因无法启动处于停用状态；仅汉兰达轿车和宇通客车取得车籍，其他车辆均无车籍。

扶余车辆问题已移送扶余纪检委另案处理。

7．部分项目配套资金不到位19,185,000.00元

至2014年5月，公主岭范家屯镇污水处理工程项目等2个项目地方配套资金不到位19,185,000.00元。其中辉南县垃圾无害化处理项目配套资金不到位4,240,000.00元，公主岭范家屯镇污水处理工程项目配套资金不到位14,945,000.00元。

不符合《中央对地方专项拨款管理办法》第十一条“应由地方安排配套资金的，应该足额安排”的规定。建议你办督促当地政府积极筹措配套资金，确保项目按计划完成。你办已接受审计建议。

8．税种使用有误，造成国家税收损失

2010年，辉南县垃圾处理项目与山东乐悟新材料工程有限公司签订供货合同。山东乐悟新材料工程有限公司负责为辉南县垃圾处理项目提供堆填场防渗材料和辅设设备，合同价款为7,669,200.00元。至2013年12月山东乐悟新材料工程有限公司供货5,143,564.36元。按国家相应税法规定，材料销售为增值税缴纳范畴，而该公司在辉南地税局按3.54%缴纳营业税，共计180,759.00元，形成混淆税种，造成国家税款流失。

不符合《税收征收管理法》第三十一条“纳税人、扣缴义务人按照法律、行政法规规定或者税务机关依照法律、行政法规的规定确定的期限，缴纳或者解缴税款”的规定。对于应缴未缴税金的问题，建议你办督促相关项目单位限期整改。你办已接受审计建议。

9．财务方面存在的问题

（1）2014年4月30日，扶余县污水处理项目专户库存现金实际盘点金额438.48元，电子现金账账面余额9,307.38元，库存现金短款8,868.90元。

不符合《现金管理暂行条例》第十二条“开户单位应当建立健全现金帐目，逐笔记载现金支付。帐目应当日清月结，帐款相符”的规定。

（2）2013年， 公主岭东区污水截流干管及市区部分排污管网改造工程项目在待摊投资中列支尚未实际支付的土地征地补偿费532,944.00元,形成多列待摊投资532,944.00元。

（3）2006年，辉南县垃圾场应急工程开工建设，于2008年全部建设完成，投资总额2,460,000.00元，该项目未单独建账，在环卫处基本户中核算。

（4）至2013年12月末，扶余县污水处理项目账龄三年以上的往来款项清理不及时，其中其他应付款合计1,015,520.31元，其他应收款合计805,399.96元。

（5）2011年至2013年，靖宇县污水处理项目在无资金申请、无工程进度情况、无建设单位、监理单位、施工单位三方确认的情况下支付给泸州七建、吉林星泰集团公司工程款。如：2011年支付星泰集团工程款4,000,000.00元，2012年支付星泰集团工程款200,000.00元，2013年支付星泰集团工程款1,500,000.00元，所附凭证中全部无资金申请、和相关支付手续。

（6）2008年至2010年，扶余县污水处理项目在没有施工方工程请款报告、工程形象进度报告，没有监理方签字的情况下，仅凭原经理签字同意支付工程或设备款，支付手续不完备。如：2010年12月，支付吉林省华兴工程建筑有限公司工程款1,000,000.00元，支付长春建设股份有限公司直属分公司工程款400,000.00元，支付中国建筑第六工程局有限公司长春分公司工程款1,000,000.00元，支付吉林省华兴工程建设集团有限公司工程款2,000,000.00元。

上述问题不符合《中华人民共和国会计法》第九条“各单位必须根据实际发生的经济业务事项进行会计核算，填制会计凭证，登记会计账簿，编制财务会计报告”的规定。

上述问题建议你办督促相关项目单位加强会计核算，调整相关会计科目。你办已接受审计建议。

（二）项目管理方面存在的问题

1．部分项目前期手续不完善

（1）长白山管委会松花江流域上游（白溪 东岗 漫江）水污染综合治理项目在池南区漫江镇林场及东岗镇建设漫江污水处理厂、漫江垃圾转运站、白溪垃圾转运站，截至2014年3月9日，项目工程已经投入使用或调试阶段，项目单位未能提供建设用地批准书。

不符合《中华人民共和国土地管理法》第四十三条“任何单位和个人进行建设，需要使用土地的，必须依法申请使用国有土地”的规定。

（2）2010年7月，靖宇县污水处理项目在未取得建设用地批准书和土地使用证的情况下，开工建设（2011年6月21日取得建设用地批准书）。截至2014年4月，项目已全部完成土建和设备安装，但一直未取得土地使用证。

不符合《土地登记办法》（国土资源部令第40号）第二十六条“依法以划拨方式取得国有建设用地使用权的，当事人应当持县级以上人民政府的批准用地文件和国有土地划拨决定书等相关证明材料，申请划拨国有建设用地使用权初始登记。新开工的大中型建设项目使用划拨国有土地的，还应当提供建设项目竣工验收报告”的规定。

上述问题建议你办督促相关项目单位限期办理相关手续。你办已接受审计建议。2014年6月，靖宇县污水处理项目国有土地使用证已办理。

2．项目管理问题

（1）项目内容申报不实

2009年，辉南县城市生活垃圾无害化处理项目取得省发改委的初步设计批复，概算金额41,470,000.00元，其中包含2006年开工建设的垃圾场应急工程，该工程实际已于2008年全部建设完成，投资额2,460,000.00元。

建议你办督促相关项目单位向原概算批复部门申请调整概算。你办已接受审计建议。

（2）部分项目进展缓慢，致使部分工程未及时投入使用

2008年7月，省发改委批复长白山管委会松花江上游水污染综合治理项目，新建污水处理站2座，垃圾转运站3座，建设工期于2009年4月开工建设，建设期一年十个月，即2011年2月应全部完工。由于部分项目开工较晚，至2013年9月，白溪污水处理厂才开始试运行、东岗垃圾转运站、白溪垃圾转运站刚建设完成并投入使用，比计划工期晚2年7个月。至2014年3月，漫江污水处理厂及垃圾转运站仍在进行设备安装，还未投入使用，比计划完工期晚3年1个月。

2010年6月，省发改委批复靖宇县污水处理项目初步设计，新建污水处理厂1座及附属设施，污水处理规模2.5万吨/日,配套建设排水管网89.56公里，新建提水泵站2座。建设工期2年项目。该项目实际于2010年7月土建动工。至2013年末，土建和设备全部完工。由于管线有漏点（修复时间2014年3月）、河北截流管线未连通、冬天天冷污水处理所需菌种培养不成功等原因，至2014年4月，靖宇县污水处理工程仍未投入使用，工程工期比批复时间拖后21个月。并且该项目可研中规定的白山（靖宇）健康产业园区尚未开发，提水泵站1座和约58公里管线未建。按目前现状，靖宇污水项目即使投入运营，污水处理量估算也仅在7000-8000吨/日，也不能达到可研中的处理规模。

（3）部分项目进度慢，造成隐性损失

2009年，吉林省发改委批准吉林省公主岭范家屯镇污水处理项目开工建设，项目投资概算87,611,100.00元，其中，利用亚洲开发银行贷款6,300,000.00美元（折合42,970,000.00元人民币），地方政府自筹42,884,500.00元。项目建设单位为吉林省国鼎市政工程集团有限公司，2009年9月经吉林省发改委批准，项目单位变更为吉林公主岭经济开发区市政工程建筑有限公司（项目建设内容和投资不变），2011年公主岭市政府批准项目建设单位变更，2013年亚行出具不反对意见函，转贷金额调整至5,960,000.00美元。由于办理上述变更手续，项目单位直到2013年才进行提款报账，截至2013年12月，累计提款4,027,803.83美元，折合人民币24,840,769.00元。按2010年结算汇率6.8282可提款27,502,650.11元，由于汇率变化，造成隐性损失约2,661,881.11元。

2009年，吉林省发改委批准吉林省公主岭市岭东区污水截流干管及市区部分排污管网改造项目可研报告，项目投资概算65,620,000.00元，其中，利用亚洲开发银行贷款4,700,000.00美元（折合32,900,000.00元人民币），地方政府自筹32,720,000.00元。项目建设单位为公主岭市城市国有资产经营有限公司。2011年5月，经省发改委批准项目单位变更为公主岭市污水截流干管工程建设管理处，由于办理变更手续，项目进展与提款报账缓慢，截至2013年12月，累计提款3,203,932.34美元，折合人民币20,609,997.47元，按2010年结算汇率6.8282可提款21,877,090.80元，汇率损失1,267,093.33元。

上述问题建议你办督促相关项目单位加快项目建设进度。你办已接受审计建议。

（4）项目已经竣工并投入使用，工程尚未决算

2009年3月，省发改委批复榆树市新建3万吨/日污水处理厂一座及附属设施项目。2010年6月该项目建成并试运营，9月正式投入使用，已完成建安投资32,601,523.00元，设备投资17,372,278.50元，待摊投资14,096,108.84元，其他投资36,450.00元，预付及应收款15,385,200.00元(扣除财政来款额度9,437,700.00元)，已完成投资合计79,491,600.00元。截至2014年5月工程尚未竣工决算。

不符合财政部关于印发《基本建设财务管理规定》的通知(财建〔2002〕394号)第三十七条“建设单位及其主管部门应加强对基本建设项目竣工财务决算的组织领导，组织专门人员，及时编制竣工财务决算。设计、施工、监理等单位应积极配合建设单位做好竣工财务决算编制工作。建设单位应在项目竣工后三个月内完成竣工财务决算的编制工作。在竣工财务决算未经批复之前，原机构不得撤销，项目负责人及财务主管人员不得调离”的规定。建议你办督促相关项目单位尽快做好竣工财务决算编制工作。你办已接受审计建议。

（5）无启动资金，污水厂处于闲置状态

截至2013年底，吉林省公主岭范家屯镇污水处理工程项目土建工程已完工，设备已安装完毕，已达到预定可使用状态，由于缺乏运行资金，污水厂一直处于闲置状态，导致范家屯镇未进行处理的污水直接排放，造成环境污染。由于概算中截流干管工程未完成，范家屯镇排放污水仍由明渠导入污水厂管线，造成环境污染。

（6）违规向个人借款 400,000.00元，未能如期偿还，致污水公司运营账户及车辆被法院查封，影响正常生产运营

2011年4月，扶余县污水处理有限公司原经理刘彦辉违规向自然人李政达借款200,000.00元，借款期限6个月，用于污水公司支付设计费等。并违规以项目车辆丰田汉兰达、牌照号吉J45679做抵押，抵押期间该车共发生违章30次，违章罚款10,550.00元。因扶余县污水公司未能如期还款，李政达将污水处理有限公司起诉至扶余县人民法院及松原市中级人民法院，市中级人民法院终审判决扶余县污水处理有限公司支付李政达200,000.00元及利息，支付李政达使用期间购买轮胎款5,530.00元，案件受理费4,375.00元由扶余县污水处理厂有限公司负担，并于2013年5月冻结、扣划扶余县污水处理厂有限公司在中国工商银行内存款250,000.00元。本案已经法院判决完毕。该车于2013年6月归还污水处理有限公司，本次审计追回机动车登记证书及车辆行车证，但李政达使用期间的违章扣分及罚款应由其处理。

2012年1月，扶余县污水处理有限公司原经理刘彦辉违规向自然人董本祥借款230,000.00元，实际只收到资金200,000.00元，30,000.00元为借款费用。用于基本户运营。因未能如期还款，董本祥将污水处理有限公司起诉至扶余县人民法院，2013年8月，扶余县法院终审判决扶余县污水处理有限公司给付董本祥230,000.00元及利息，案件受理费4,750.00元、保全费1,720.00元由扶余县污水处理有限公司负担，并冻结、扣划扶余县污水处理有限公司在中国工商银行内存款250,000.00元。

至2014年5月15日，因董本祥起诉至法院，扶余污水公司账户无资金偿还，现公司车辆及银行账户被法院查封，不能正常开展财务工作及生产运营。

上述问题建议你办督促相关项目单位与政府、财政等相关部门沟通协商，争取资金尽早让污水厂正常生产运营。你办已接受审计建议。

（三）上一年度审计发现问题未整改情况

审计发现，上一年度审计报告中披露的12个问题中，部分项目超概算、长白山开发建设（集团）有限责任公司超进度拨付设计费、公主岭国有资产经营公司弄虚作假虚增上级拨入资金、部分项目单位挪用项目资金、部分项目单位应缴未缴税金、部分项目前期手续不完善、部分项目进展缓慢、长白山管委会水污染综合治理项目提款报账进度较慢、部分项目工程成本不实等9个问题未全部整改，本年度仍然存在。建议你办应切实制定和落实整改措施，完善制度，加强管理，促进项目顺利实施。你办已接受审计建议。

III. Audit Findings and Recommendations

Audit Findings and Recommendations

In addition to performing the audit and expressing an opinion on the financial statements, we also make observations with respect to compliance with applicable provisions of state laws and regulations and the loan agreement of the relevant entities, its internal financial control and project management, project performance and the follow-up of previous recommendations during the project implementing process. We found the following issues:

Non-compliance with state laws and regulations or the applicable provisions of the Loan Agreement

- Some projects with overestimates, totaling of RMB 20,954,874.17 yuan

By May 2014, some expenses for four projects including Jingyu County Wastewater Treatment Project have exceeded the cost estimates, totaling of RMB 20,954,874.17 yuan, of which RMB 2,768,300.00 yuan for the third street, the third road, the fourth street and the fourth road subprojects of Changbai Mountain Management Committee Songhua River Basin Upstream (Baixi, Donggang and Manjiang) Integrated Water Pollution Treatment Road Project, RMB 3,539,535.00 yuan for the vehicles of Huinan County Solid Waste Treatment Project, RMB 681,939.17 yuan for the unit management fee of Jingyu County Wastewater Treatment Project, RMB 13,965,100.00 yuan for construction and installation engineering and purchasement of equipment installation of Gongzhuling Fanjiatun Town Wastewater Treatment Project.

It isn’t in conformity with the provisions of the Article 11, Several Provisions on Improvement of the Cost Estimate and Budget in the Engineering Construction (JB[1983] No.1038) which stipulates that any department and any unit should strictly execute the approved total cost estimate and can’t exceed the limits at will. We suggest that your PMO should urge the relevant IAs to respectively submit the application for adjusting their cost estimate to the unit which approved the original cost estimate. Your PMO has accepted the audit recommendation. In June 2014, the issue related to the overestimate for the unit management fee for Jingyu County Wastewater Treatment Project has been rectified.

2．Failure of inviting bids before the project construction

In July 2010, in order to build a new Wastewater Treatment Plant and make it put into operation in the same year, through the discussion at the meeting of the county magistrate, Jingyu County Government made a decision that Luzhou City No.7 Construction Engineering Company, Jingyu Branch (hereinafter called as “Luzhou Qijian”) constructed the civil works and pipe networks of the Wastewater Plant firstly. In Nov. 2010, in the bidding process, Luzhou Qijian failed to win the bid and the successful bidder was Jilin Xingtai Company. So Jilin Xingtai Company took over the construction. By the early of 2012, the project fund of RMB 52,900,000.00 yuan has been paid to Luzhou Qijian, of which RMB 8,000,000.00 yuan with invoices and the remaining RMB 44,900,000.00 yuan without invoices. The money was charged to Prepaid Project Funds instead of the Construction and Installation Investment.

It isn’t in conformity with the provisions in the Article 3, the Bidding Law of the People's Republic of China which stipulates that such construction projects as survey, design, construction, supervision and the purchasement of key equipments and materials related to construction within the territory of the People’s Republic of China should invite for bids: (Ⅰ) large infrastructure projects and public utilities projects related to social public benefits and public security; (Ⅱ) projects fully or partially financed by the state-owned funds or by the country; (Ⅲ) projects financed by the loans or grants from the international organization or foreign government. We suggest that your PMO should urge the IA to strictly execute the provisions in the Bidding Law. Such problem should be prohibited. Your PMO has accepted the audit recommendation.

3．Misappropriation of the project construction funds to pay RMB 380,996.00 yuan for salaries of the temporary employees and employees with public welfare posts

From 2011 to 2014, for Jingyu County Wastewater Treatment Plant, the salaries of RMB 380,996.00 yuan has been disbursed out of the Deferred Investment, of which RMB 230,996.00 yuan for the salaries of the temporary employees and RMB 150,000.00 yuan for employees with public welfare posts. The project construction funds were misappropriated to pay RMB 230,996.00 yuan for the salaries of the temporary employees and RMB 150,000.00 yuan for employees with public welfare posts.

It isn’t in conformity with the provisions of the Article 28, Methods on Management of Loans and Grants from the International Financial Organization and Foreign Government issued by the Ministry of Finance (No.38 Order of Ministry of Finance in 2006) which stipulates that the loan proceeds should be used in accordance with the provisions in the loan legal documents, which shouldn’t be stranded, incepted and misappropriated for any excuses or in any forms or change the purposes of the loan proceeds without authorization. We suggest that your PMO should urge the relevant IA to return the project construction funds. Your PMO has accepted the audit recommendation. In June 2014, Jingyu County Government has made up for the misappropriated special funds with the counterpart funds of RMB 380,996.00 yuan.

4．Overpayment RMB 78,100.00 yuan for vehicles and RMB 10,000.00 yuan for training when purchasing the vehicles without following the requirements of the cost estimate.

In Dec. 2010, the bids were opened publicly for purchasing the vehicles for Jingyu County Wastewater Treatment Project, the successful bidder was Heilongjiang Province Huacheng Environmental Protection and Energy Saving Engineering Co., Ltd. and the contract price was RMB 1,986,620.00 yuan. By April 2014, the ADB has paid the full amount for the vehicles directly. According to the stipulations in the contract, it said that a vehicle with the price of RMB 385,000.00 yuan and a water quality detection vehicle with the price of RMB 295,800.00 yuan should be purchased. But the above vehicles with the price of RMB 680,800.00 yuan weren’t purchased. Actually, the total amount of RMB 602,700.00 yuan were used for purchasing the vehicles, of which RMB 239,800.00 yuan for a Honda CRV2.4, RMB 322,900.00 yuan for a Buick commercial vehicle and RMB 40,000.00 yuan for a Wuling van. RMB 78,100.00 yuan was overpaid for vehicles when purchasing the vehicles without following the requirements of the cost estimate. In the contract, it stipulated that the payment for vehicles included RMB 10,000.00 yuan for training. In the course of the implementation of the contract, Heilongjiang Huacheng Company didn’t provide the corresponding training and overpaid RMB 10,000.00 yuan for training.

It isn’t in conformity with the Contract for Purchasing the Vehicles of Jingyu County Wastewater Treatment Project and the Article 14, Tentative Provisions on Audit Sanctions for Construction Projects which stipulates when settlement of the project cost, whether it was more than or less than the original project cost, it should be adjusted. We suggest that your PMO should urge the IA to purchase vehicles in accordance with the contract and take back the overpayment for the vehicles. Your PMO has accepted the audit recommendation. In June 2014, the supplier has returned the overpayment for the vehicles of RMB 78,100.00 yuan.

5．Overpayment RMB 30,000.00 yuan for the equipment

In June 2010, the bids were opened publicly for purchasing a set of the daily leachate treatment equipment for Huinan County Solid Waste Treatment Project and the successful bidder was Beijing Tiandiren Environmental Protection & Science and Technology Co., Ltd. By the audit date, the IA has paid RMB 4,340,100.00 yuan for the equipment in full amount in accordance with the contract, of which RMB 30,000.00 yuan for domestic tour. Because Beijing Tiandiren Environmental Protection & Science and Technology Co., Ltd. didn’t provide the service for the domestic tour, RMB 30,000.00 yuan was overpaid for the equipment.

It isn’t in conformity with the Contract for Purchasing the Equipment of Huinan County Solid Waste Treatment Project and the Article 14, Tentative Provisions on Audit Sanctions for Construction Projects which stipulates when settlement of the project cost, whether it was more than or less than the original project cost, it should be adjusted. We suggest that your PMO should urge the IA to take back the overpayment for the equipment. Your PMO has accepted the audit recommendation.

6．The successful bidder failed to strictly execute the purchasement contract. The former captain of team of Fuyu County Wastewater Company and the other persons were involved in purchasing the vehicles. Compared with the vehicles in the contract, the actually purchased vehicles had the different parameters, especially, reduced the main parameters.

（1）On June 29, 2010 and Dec. 23, 2010, under the circumstances of failure of receiving the vehicles purchased by Fuyu County Wastewater Treatment Project, subject to the signature and consent of Mr. Liu Yanhui, the former manager of Fuyu County Wastewater Company, RMB 920,000.00 yuan and RMB 100,000.00 yuan (the total amount of RMB 1,020,000.00 yuan) for the vehicles were illegally paid to the successful bidder – Zhongjing Dongyuan Company in advance respectively. In the contract, it stipulated that after receiving the proforma invoice from the successful bidder, 30% of the contract price would be paid in advance and after receiving all the goods and passing the acceptance, the remaining 70% of the contract price be paid. The successful bidder didn’t execute the Purchasement Contract and transferred the purchasement of vehicles to Mr. Sheng Xiaoming, the former captain of team of the Wastewater Company. As Mr. Sheng Xiaoming confirmed, Mr. Cai Ming, who was the representative of Zhongjing Dongyuan Company, contacted him to purchase the vehicles. A Purchasement Contract was signed with Fuyu County Sanchahe Ruilin Auto Repair Factory (the same parameters as those in the original contract) and the contract price was RMB 920,000.00 yuan. Actually, the vehicles were purchased by Mr. Sheng Xiaoming (As the manager, Mr. Liu Yanhui knew this matter.) On July 12, 2010, RMB 920,000.00 yuan for purchasing the vehicles was transferred from Zhongdong Jingyuan Company to Fuyu County Sanchahe Ruilin Auto Repair Factory and then all the money was transferred to the personal card of Mr. Sheng Xiaoming (Fuyu Zhanqian Sub-branch, Agricultural Bank of China, card number: 6228483730135573813) on July 26, 2010. Mr. Sheng Xiaoming took out all the money from the card from July 27, 2010 to Dec. 21, 2012 (There was no balance in the card until June 25, 2013). The money was mainly used for purchasing 5 vehicles including a FAW Liberation Dump Truck, a second-hand Ravel Dump Truck, a Zhengzhou Yutong Passenger Car, a Toyota Highlander car, a forklift and handling the relevant formalities. Except for the Toyota Highlander car, all the other vehicles had the different parameters with those stipulated in the contract and reduced the main parameters. Subject to the consent of Mr. Liu Changwen, the former Head of Fuyu County Housing and Urban-rural Construction Bureau and Mr. Liu Yanhui, the former manager of Fuyu County Wastewater Company, Mr. Sheng Xiaoming purchased that second-hand Ravel Dump Truck which was an old Ravel 140 Dump Truck owned by both Mr. Wang Jiye and Mr. Sun Zhenyu. They were the relatives of Ms. Meng Kuili who was the accountant of Fuyu County Housing and Urban-rural Construction Bureau. It took the place of a FAW Liberation Dump Truck in the contract (the contract price of RMB 167,900.00 yuan). As Mr. Sheng Xiaoming and Mr. Wang Jiye confirmed, its fixed price was RMB 100,000.00 yuan that was paid in cash to Mr. Wang Jiye by Mr. Sheng Xiaoming. There were no receipts or contract for the transaction and the seller didn’t provide the invoices. Until May 2014, its ownership hasn’t been transferred yet. Now it has been parking within the yard of Fuyu County Wastewater Company. As Mr. Liu Yanhui, the former manager of Fuyu County Wastewater Company confirmed, it was used for transportation of earthwork and sludge and so on. As Mr. Wu Jun, the current Person in charge of Fuyu County Wastewater Company confirmed, since he assumed office in July 2012, it hadn’t been used due to failure to start.

（2）On Sept. 29, 2010, China National Heavy Machinery Corporation, which was the successful bidder for purchasing a forklift truck for Fuyu County Wastewater Company, didn’t fulfill the duties for the purchasement and transferred the purchasement of the forklift truck to Mr. Sheng Xiaoming. Then RMB 297,105.00 yuan for purchasing the forklift truck was transferred to Fuyu County Sanchahe Xinxing Hardware Store, which was withdrawn in full amount by Mr. Sheng Xiaoming. One forklift truck was purchased from Songyuan City with the lower main parameters compared with those in the contract. As Mr. Sheng Xiaoming confirmed, Mr. Cai Ming, the representative of China National Heavy Machinery Corporation - the successful bidder, contacted him to purchase the forklift truck for Fuyu County Wastewater Company in the Processing Equipment Purchasement Contract.

As Mr. Sheng Xiaoming confirmed, except for the second-hand Ravel Dump Truck, there were invoices for purchasing the remaining vehicles but the invoices couldn’t be provided for neglect of finding the invoices. The contract price for purchasing the vehicles between Fuyu County Wastewater Company and the successful bidder was RMB 1,310,000.00 yuan but for Fuyu Wastewater Company, the vehicles were actually purchased by Mr. Sheng Xiaoming. After the audit team surfed the internet to inquiry the prices, they found out that the lowest price was RMB 873,800.00 yuan and the highest price RMB 1,006,600.00 yuan. Since the parameters for the actually purchased vehicles were different with those for the vehicles in the contract, this might lead to the balance of RMB 303,400.00 yuan or RMB 436,200.00 yuan between the lowest price and the highest price (It couldn’t be found out the specific amount due to the limited audit means.) These were suspected to cause the losses of the state-owned assets or cheat the state-owned assets by the relevant staffs.

Six vehicles of Fuyu County Wastewater Company purchased by Mr. Sheng Xiaoming had no receipts and no acceptance certificates. There were only proforma invoices provided by the successful bidder. The formal invoices weren’t provided in accordance with the provisions of the national tax law. Since there weren’t the formal invoices, the payment for the above-mentioned vehicles was charged to the Prepaid Project Funds by Fuyu Wastewater Company and the asset management for the vehicles couldn’t be carried out. After the physical inventory and confirmation by the relevant staffs, the FAW Liberation Dump Truck, the forklift truck, the Yutong Passenger Car and the forklift could be used normally. Since the Wastewater Company was involved in the economic disputes, the Toyota Highlander car was sealed up by the Fuyu City Court. Now the second-hand Ravel Dump Truck was still registered under the name of the seller. Due to failure to start, it remained in the inactive state. Only Highlander car and Yutong Passenger Car have been registered and the remaining vehicles haven’t been registered yet.

Fuyu vehicles matters have been transferred to Fuyu Commission for Discipline Inspection and settled in a separate case.

7．Some projects without the counterpart funds of RMB 19,185,000.00 yuan in place

By May 2014, for Gongzhuling Fanjiatun Town Wastewater Treatment Project and the other project, the local counterpart funds of RMB 19,185,000.00 yuan haven’t been in place, of which RMB 4,240,000.00 yuan for Huinan County Solid Waste Harmless Treatment Project and RMB 14,945,000.00 yuan for Gongzhuling Fanjiatun Town Wastewater Treatment Project.

It isn’t in conformity with the Article 11, Methods on Administration of the Special Appropriation from the Central Government to the Local which stipulates that the counterpart funds should be provided in full amount. We suggest that your PMO should urge the local governments to actively raise the counterpart funds to ensure that the projects can be completed as planned. Your PMO has accepted the audit recommendation.

8．Something was wrong with taxes, which caused the losses of the national revenues.

In 2010, Huinan County Solid Waste Treatment Project and Shandong Lewu New Materials Engineering Company signed a Supply Contract. Shandong Lewu New Materials Engineering Company would be responsible for supplying landfills impervious materials and auxiliary equipments to Huinan County Solid Waste Treatment Project with the contract price of RMB 7,669,200.00 yuan. By Dec. 2013, the goods with the price of RMB 5,143,564.36 yuan have been supplied by Shandong Lewu New Materials Engineering Company. According to the relevant provisions of the national tax law, material sales should fall into a scope of value-added tax. But the company only paid the business tax at the rate of 3.54%, totaling of RMB 180,759.00 yuan. This formed to confuse the taxes and caused the losses of the national revenues.

It isn’t in conformity with the provisions of the Article 31, Law on the Administration of Tax Collection which stipulates that taxpayers and withholding agents should pay the taxes or remit the taxes in accordance with the laws and administrative rules or the identified term specified by the tax authorities in accordance with the laws and administrative rules. For payment of the unpaid taxes, we suggest that your PMO should urge the relevant IAs to make the supplementary payment for the unpaid taxes before the deadline. Your PMO has accepted the audit recommendation.

9． Financial Matters

（1）On April 20, 2014, for Fuyu County Wastewater Treatment Project, the actual amount of cash inventory account was RMB 438.48 yuan and the electronic cash balance RMB 9,307.38 yuan. So the cash inventory was short of RMB 8,868.90 yuan.

It isn’t in conformity with the Article 12, Tentative Regulations on Cash Management which stipulates that the account opening unit should establish the sound cash account, record cash payments one by one and make account agree with cash.

（2） In 2013, for Gongzhuling sewage inception pipes in the eastern zone and some sewage pipe network renovation project in the urban zone, the compensation for the land acquisition of RMB 532,944.00 yuan, which hasn’t been paid yet, was disbursed out of the Deferred Investment. RMB 532,944.00 yuan was overpaid under the Deferred Investment.

（3）With the total investment of RMB 2,460,000.00 yuan, Huinan County Landfill Emergency Project started to construct in 2006 and completed in 2008. This project was accounted in the basic accounting of the Sanitation Division instead of establishing a separate account.

（4）By the end of Dec. 2013, for Fuyu County Wastewater Treatment Project, over-three-year transactions haven’t been cleared up timely including RMB 1,015,520.31 yuan for Other Payables and RMB 805,399.96 yuan for Other Receivables.

（5）From 2011 to 2013, Jingyu County Wastewater Treatment Project paid the project funds to Luzhou Qijian and Jilin Xingtai Group without the fund application, progress of the project and confirmation by three parties – the Employer, supervision unit and construction unit. For example, the project funds of RMB 4,000,000.00 yuan, RMB 200,000.00 yuan and RMB 1,500,000.00 yuan were paid to Xingtai Group in 2011, in 2012 and in 2013 respectively. There weren’t fund applications and the relevant payment formalities in the attached documents.

（6）From 2008 to 2010, subject to the signature and consent of the former manager, for Fuyu County Wastewater Treatment Project, the money for the project or equipments was paid without the engineering request report and the project progress report from the construction unit and the signature of the supervision unit. The payment formalities were incomplete. For example, in Dec. 2010, the project fund of RMB 1,000,000.00 yuan was paid to Jilin Province Huaxing Engineering Construction Co., Ltd., the project fund of RMB 400,000.00 yuan was paid to the Branch Company of Changchun Construction Co., Ltd., the project fund of RMB 1,000,000.00 yuan was paid to China Construction Sixth Engineering Bureau Co., Ltd., Changchun Branch and the project fund of RMB 2,000,000.00 yuan was paid to Jilin Province Huaxing Engineering Construction Co., Ltd.

It isn’t in conformity with the provisions of the Article 9, Accounting Law of the People's Republic of China which stipulates that any unit must carry out the accounting calculation, fill in the accounting documents, register the accounting books and prepare the accounting report on the base of the economic transaction matters that actually occurred.

For the above matters, We suggest that your PMO should urge the relevant IAs to strengthen the accounting and adjust the relevant account titles. Your PMO has accepted the audit recommendation.

Issues on project management

1． Incomplete preparation formalities for some projects

（1）Changbai Mountain Management Committee Songhua River Basin Upstream (Baixi, Donggang and Manjiang) Integrated Water Pollution Treatment Project included construction of Manjiang Wastewater Treatment Plant, Manjiang Solid Waste Transfer Station, Baixi Solid Waste Transfer Station at Manjiang Town Forestry of Chinan District and at Donggang Town. By March 9, 2014, the subprojects have been put into operation or commissioning but the IA couldn’t provide the approval letter for land use for construction.

It isn’t in conformity with the provisions of the Article 43, Methods on Management of Land of the People’s Republic of China which stipulates that any unit or individual should apply for use of the states-owned land before construction if the land is needed.

（2）In July 2010, Jingyu County Wastewater Treatment Project started to construct without obtaining the approval letter for land use for construction and the land use certificate (The approval letter for land use for construction was obtained on June 21, 2011.). By April 2014, the project hasn’t obtained the land use certificate after all the civil works and installation of equipments of the project have been completed.

It isn’t in conformity with the provisions of the Article 26, Methods on Land Registration (No.40 Order issued by the Ministry of Land and Resources) which stipulates that the state-owned construction land use right is obtained through allocation by law, the party concerned should apply for the initial registration for the allocated state-owned construction land use right with the relevant evidential materials such as land use document and state-owned land allocation decision letter approved by the People’s Government at or above the county level. When the large and medium-sized construction projects which use the allocated state-owned land start to construct, they should provide the completion acceptance report of the construction project.

For the above matters, We suggest that your PMO should urge the IAs to handle the relevant formalities before the deadline. Your PMO has accepted the audit recommendation. In June 2014, the state-owned land use certificate  for Jingyu County Wastewater Treatment Project has been obtained.

2．Issues on project management

(1)Application for untrue project contents

In 2009, Huinan County Urban Solid Waste Harmless Treatment Project obtained the approval of the preliminary design by Jilin DRC with the cost estimate of RMB 41,470,000.00 yuan, which included the Landfill Emergency Project. The Landfill Emergency Project was built in 2006 and completed in 2008 with the total investment of RMB 2,460,000.00 yuan.

We suggest that your PMO should urge the relevant IA to submit an application for adjustment of the cost estimate to the department which approved the original cost estimate. Your PMO has accepted the audit recommendation.

（2）Some projects had too slow progresses to be put into operation in time.

In July 2008, Jilin DRC approved Changbai Mountain Management Committee Songhua River Basin Upstream Integrated Water Pollution Treatment Project. It included newly construction of two wastewater treatment stations and three garbage transfer stations. The construction period lasted one year and ten months from April 2009 to Feb. 2011. Because some subprojects started relatively late, Baixi Wastewater Treatment Plant started to commissioning and Donggan Solid Waste Transfer Station and Baixi Solid Waste Transfer Station were just constructed and put into operation until Sept. 2013. This was two years and seven months later than the schedule. By March 2014, for Manjiang Wastewater Treatment Plant and Solid Waste Transfer Station, the installation of the equipments was still under way and it hasn’t been put into operation yet. This was three years and one month later than the scheduled completion date.

In June 2010, Jilin DRC approved the preliminary design of Jingyu County Wastewater Treatment Project which included newly construction of one wastewater treatment plant with the daily treatment capacity of 2500 tons and auxiliary facilities, construction of drainage pipe network with the length of 89.56 km and newly construction of two pumping stations. The construction period was two year. The project actually started to construct in July 2010. By the end of 2013, the civil works and equipments had been completed. Due to leakage points in the pipelines (repair date: March 2014), disconnection of inception pipelines in the northern part of the river and failure of bacterial culture needed by wastewater treatment due to the cold weather in winter, Jingyu County Wastewater Treatment Project hasn’t been put into operation by April 2014. The project period was delayed 21 months later than the approved date. As mentioned in the FSR of the project, Baishan (Jingyu) Health Industrial Park hadn’t been developed and one pumping station and pipelines with the length of about 58 km hadn’t been built. Under the current circumstances, even if Jingyu Wastewater Project was put into operation with the estimated wastewater treatment capacity of 7000 to 8000 tons per day, it couldn’t realize the treatment capacity in the FSR.

（3）Some projects with slow progresses caused the recessive losses.

In 2009, Jilin DRC approved Jilin Province Gongzhuling Fanjiatun Town Wastewater Treatment Project started to construct. The cost estimate was RMB 87,611,100.00 yuan, of which USD 6,300,000.00 for ADB financing (equivalent to RMB 42,970,000.00 yuan) and RMB 42,884,500.00 yuan for the local government financing. The IA was Jilin Province Guoding Municipal Engineering Group Co., Ltd. In Sept. 2009, subject to the approval of Jilin DRC, it was changed to Jilin Gongzhuling Economic Development Zone Municipal Engineering Construction Co., Ltd. (the same project scope and the same cost estimate). Gongzhuling Municipal Government approved the change in the IA in 2011, and the ADB issued the no-objection letter on this matter in 2013. The loan amount was adjusted to USD 5,960,000.00. Since the above change was needed to handle the formalities, the IA didn’t submit the withdrawal application until 2013. By Dec. 2013, the accumulative withdrawals had reached USD 4,027,803.83（equivalent to RMB 24,840,769.00 yuan）. The above accumulative amount should be RMB 27,502,650.11 yuan on the base of the exchange rate in 2010, that is, USD 1= RMB 6.8282 yuan. Due to change in the exchange rate, it caused the recessive losses of about RMB 2,661,881.11 yuan.

In 2009，Jilin DRC approved the FSR of Gongzhuling sewage inception pipes in the eastern zone and some sewage pipe network renovation project. The cost estimate was RMB 65,620,000.00 yuan, of which USD 4,700,000.00 for ADB financing (equivalent to RMB 32,900,000.00 yuan) and RMB 32,720,000.00 yuan for the local government financing. The IA was Gongzhuling City Urban State-owned Management Co., Ltd. In May 2011, subject to the approval of Jilin DRC, the IA was changed to Gongzhuling City Sewage Inception Pipes Project Management Office. Since the above change was needed to handle the formalities, the project was slow in the progresses and disbursement. By Dec. 2013, the accumulative withdrawals had reached USD 3,203,932.34（equivalent to RMB 20,609,997.47 yuan）. The above accumulative amount should be RMB 21,877,090.80 yuan on the base of the exchange rate in 2010, that is, USD 1= RMB 6.8282 yuan. Due to change in the exchange rate, it caused the recessive losses of about RMB 1,267,093.33 yuan.

For the above matters, we suggest that your PMO should urge the relevant IAs to quicken the project implementation. Your PMO has accepted the audit recommendation.

（4）Project has been completed and put into operation but it hasn’t completed the final settlement yet.

In March 2009, Jilin DRC approved Yushu City to construct a new wastewater plant with the daily treatment capacity of 30,000 tons and auxiliary facilities. In June 2010, the project was completed and carried out commissioning. In Sept. 2010, it was formally put into operation. The Investment in Construction and Installation has been reached RMB  32,601,523.00 yuan, Investment in Equipments RMB 17,372,278.50 yuan, Deferred Investment RMB 14,096,108.84 yuan, Other Investments RMB 36,450.00 yuan，Prepaid & Receivables RMB 15,385,200.00 yuan (deduction of the money from the government finance of RMB 9,437,700.00 yuan)， and the total completed investment RMB 79,491,600.00 yuan. By May 2014, the project hasn’t the final settlement yet.

It isn’t in conformity with the Article 37, the Notice on Basic Construction Financial Management Regulations (CJ [2002] No.394) issued by the Ministry of Finance which stipulates that the Employer and its department in charge should strengthen the organization and leadership in the financial settlement, ask the special persons to prepare the financial settlement in time for the completion of the basic construction projects. The design unit, construction unit and supervision unit should actively coordinate with the building unit to prepare the financial settlement of the completion. The Employer should complete the preparation of the financial settlement of the completion within three months after the project was completed. The original organ shouldn’t be cancelled and the person in charge and financial officer shouldn’t be moved to another job before the financial settlement of the completion was approved. We suggest that your PMO should urge the relevant IA to prepare the financial settlement of the completion as quickly as possible. Your PMO has accepted the audit recommendation.

（5）Wastewater Plant was in an idle state due to no start-up funding

By the end of 2013, Jilin Province Gongzhuling Fanjiatun Town Wastewater Treatment Project has completed the civil works and equipment installation, which has reached the expected usable condition. But due to shortage of the operational funding, the wastewater plant has been in an idle state. This made the wastewater which wasn’t treated at Fanjiatun Town be discharged directly to pollute the environment. The inception pipes haven’t been completed in the budget yet so the wastewater at Fanjiatun Town still was discharged from the open channel to the pipelines of the wastewater plant, which caused the environmental pollution.

（6）RMB 400,000.00 yuan was borrowed from an individual illegally and the money wasn’t repaid as schedule. This made the operational account and the vehicle of the wastewater company be sealed up by the Court so that it affected the normal production and operation.

In April 2011, Mr. Liu Yanhui, the former manager of Fuyu County Wastewater Treatment Co., Ltd., borrowed RMB 200,000.00 yuan from Mr. Li Zhengda who was a natural person with the loan term of six months which would be used for payment of the design expenses and so on. Toyota Highlander with the license plate number: Ji J45679 was mortgaged illegally. During the period of mortgage, it broke traffic regulations for 30 times with the penalty of RMB 10,550.00 yuan. Because Fuyu County Wastewater Plant didn’t repay as schedule, the company was prosecuted by Mr. Li Zhengda to Fuyu County People’s Court and Songyuan City Intermediate People’s Court. Songyuan City Intermediate People’s Court finalized that Fuyu County Wastewater Treatment Plant should pay RMB 200,000.00 yuan, interests and RMB 5,530.00 yuan for tire to Mr. Li Zhengda and bore the case acceptance fee of RMB 4,375.00 yuan. In 2013, RMB 250,000.00 yuan was frozen and deducted, which was deposited in the Industrial and Commercial Bank of China by Fuyu County Wastewater Treatment Plant Co., Ltd. The case has been finalized by the court. This vehicle was returned to the Wastewater Treatment Co., Ltd. in June 2013. After the auditing, the motor vehicle registration certificate and vehicle driving license were retrieved but Mr. Li Zhengda should be responsible for the illegal deduction and penalty when he used the vehicle.

In Jan. 2012, Mr. Liu Yanhui, the former manager of Fuyu County Wastewater Treatment Co., Ltd., borrowed RMB 230,000.00 yuan from Mr. Dong Benxiang who was a natural person illegally. The actual loan was RMB 200,000.00 yuan and the remaining RMB 30,000.00 yuan for cost of borrowing. The money would be used for operation of the basic account. Because the money wasn’t repaid as schedule, the company was prosecuted by Mr. Dong Benxiang to Fuyu County People’s Court. In August 2013, Fuyu County People’s Court finalized that Fuyu County Wastewater Treatment Plant should pay RMB 230,000.00 yuan and interests to Mr. Dong Benxiang and bore the case acceptance fee of RMB 4,750.00 yuan and perservaion fee of RMB1,720.00 yuan. RMB 250,000.00 yuan was frozen and deducted, which was deposited in the Industrial and Commercial Bank of China by Fuyu County Wastewater Treatment Plant Co., Ltd.

Up to May 15, 2014, since the company was prosecuted to the Court by Mr. Dong Benxiang, there was no money to pay the debts in the account of Fuyu Wastewater Company. Now the vehicle and bank account were sealed up by the Court, the company couldn’t normally carry out the financial work and production and operation.

For the above matters, We suggest that your PMO should urge the IA to communicate with the government, financial department and the other relevant department and try the best to ask for the money to make the wastewater plant produce and operate normally as early as possible. Your PMO has accepted the audit recommendation.

The Followed-up of previous recommendations

According to the audit, among 12 issues disclosed in the audit report of last year, there are 9 issues haven’t been corrected and they still existed in the current year including some projects with the overestimate, Changbai Mountain Development & Construction (Group) Co., Ltd.: appropriation of the design expenses ahead of schedule, Gongzhuling State-owned Assets Management Company: fraudulently increasing the appropriation funds, some IAs with the misappropriation of the project cost, some IAs with unpaid tax payable, some IAs with unpaid tax payable, slow progress for some projects, Integrated Water Pollution Treatment Project of Changbai Mountain Management Committee with the slow progress in the disbursement and some projects with the untrue project costs. We suggest that your PMO should practically formulate and implement measures for rectification, improve the system, enhance management and promote smooth implementation of the project. Your PMO has accepted the audit recommendations.